## IDS
Sub area |  | Scheme information |  |  | Categorisation |  |  |  | Cost and delivery
Relevant Sub area | Site/Sub area attribution | Ref | Scheme name | Scheme description | Infrastructure category | Infrastructure sub-category | Source | Prioritisation | Cost (£) | Source of cost | Confirmed funding | Potential funding mechanism | Initial phasing | Potential Delivery partners/ providers | Commentary | Working Commentary (to be deleted) | Sensitive to growth figure | Status of agreement (to be deleted)
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 1.112 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 1.113 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 1.114 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 1.115 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 1.116 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 1.117 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 1.118 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | 1.219 | Land north of Mickleton Primary school | 2FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 9148860 | GCC Education (Benchmark per primary pupil of £24,660) and an estimated 371 pupils | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs | Additional funding to deliver total growth to be provided by growth in sub area/ captured under item 1.311 and 1.312 |  | Yes | Agreed in principle
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | 1.119 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 1.21 | Land north, east and south of Moreton-in-Marsh | 3 FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 16423560 | GCC Education (Benchmark per primary pupil of £24,660) and estimated 666 pupils | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs | Additional funding to deliver total growth to be provided by growth in sub area/ captured under item 1.311 and 1.312 |  | Yes | Agreed in principle
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 1.22 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
District-wide | All sites | 1.122 | Assess Local capacity at application stage | Support within nearby local centre | 01_Education | 01_Early years | IDP modelling | Important | Planning obligation | GCC early years | N/A | S106; commercial funding | 06: 2027-2043 (inclusive) | GCC; Private sector provider |  |  | No | Agreed in principle
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 1.212 | Steading Southern Extension Primary school | 1FE Primary school (with and additional 1FE to be delivered to cover growth beyond Plan period) | 01_Education | 01_Primary | IDP modelling | Essential | 10085940 | GCC Education (Benchmark per primary pupil of £24,660) and estimated 409 pupils (an estimated 176 pupils in the plan period) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs | Additional funding to deliver total growth to be provided by growth in sub area/ captured under item 1.311 and 1.312 |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 1.213 | Land south east of Cirencester and south of Preston Primary school | 2FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 10135260 | GCC Education (Benchmark per primary pupil of £24,660) and an estimated 410 pupils | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs | Additional funding to deliver total growth to be provided by growth in sub area/ captured under item 1.311 and 1.312 |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 1.214 | Land east of Kingshill Lane Primary School | 1FE Primary school (with land for expansion to 2FE) | 01_Education | 01_Primary | IDP modelling | Essential | 4537440 | GCC Education (Benchmark per primary pupil of £24,660) and an estimate 184 pupils | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs | Additional funding to deliver total growth to be provided by growth in sub area/ captured under item 1.311 and 1.312 |  | Yes | Agreed in principle
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 1.215 | Land surrounding Down Ampney Primary school | 3FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 12280680 | GCC Education (Benchmark per primary pupil of £24,660) and an estimated 498 pupils | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs | Additional funding to deliver total growth to be provided by growth in sub area/ captured under item 1.311 and 1.312 |  | Yes | Agreed in principle
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 1.216 | Land south of Driffield Primary school | 2FE Primary school (room for expansion to 3FE to serve broad location for growth) | 01_Education | 01_Primary | IDP modelling | Essential | 16448220 | GCC Education (Benchmark per primary pupil of £24,660) and an estimated 667 pupils, with 327 in the plan period | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs | Additional funding to deliver total growth to be provided by growth in sub area/ captured under item 1.311 and 1.312 |  | Yes | Agreed in principle
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 1.217 | Land north-east of Fairford Primary school | 2FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 8458380 | GCC Education (Benchmark per primary pupil of £24,660) and an estimated 343 pupils | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs | Additional funding to deliver total growth to be provided by growth in sub area/ captured under item 1.311 and 1.312 |  | Yes | Agreed in principle
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 1.218 | Land south-west of Kemble Primary school | 2FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 7545960 | GCC Education (Benchmark per primary pupil of £24,660) and an estimated 306 pupils | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs | Additional funding to deliver total growth to be provided by growth in sub area/ captured under item 1.311 and 1.312 |  | Yes | Agreed in principle
North Cotswold | North Cotswold Sub area | 1.221 | Financial contributions towards primary delivery | Financial contributions to support delivery of local school expansion (where not provided by strategic sites) | 01_Education | 01_Primary | IDP modelling | Essential | 11047680 | GCC Education (Benchmark per primary pupil of £24,660) and an estimated 448 pupils, including non-strategic sites | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
South Cotswold | South Cotswold Sub area | 1.222 | Financial contributions towards primary delivery | Financial contributions to support delivery of local school expansion (where not provided by strategic sites) | 01_Education | 01_Primary | IDP modelling | Essential | 17459280 | GCC Education (Benchmark per primary pupil of £24,660) and an estimated 708 pupils, including non-strategic sites | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | All sites | 1.311 | South Cotswold new Secondary | 6FE Secondary school (room for expansion) to be delivered on Land South East of Cirencester and south of Preston | 01_Education | 01_Secondary | IDP modelling | Essential | See site totals to avoid double counting | GCC Education (Benchmark per Secondary pupil of £29,875 for 900) for £26,887,500 | 0 | S106; DfE grant | 03: 2033-2037 (inclusive) | GCC; existing MATs | Qualifying sites to contribute to new provision on identified site |  | Yes | Agreed in principle
Moreton-in-Marsh | All sites | 1.312 | North Cotswold new Secondary | 6FE Secondary school (with contributions in line with mitigation / support wider re-distribution of students travelling to Chipping Camden) to be delivered at Moreton in Marsh | 01_Education | 01_Secondary | IDP modelling | Essential | See site totals to avoid double counting | GCC Education (Benchmark per Secondary pupil of £29,875 for 900) for £26,887,500 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs | Qualifying sites to contribute to new provision on identified site |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 1.314 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 6004875 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 201, 86 within the plan period | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 1.315 | Secondary Financial contributions | Financial contributions provided to deliver onsite secondary school | 01_Education | 01_Secondary | IDP modelling | Essential | 6034750 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 202 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 1.316 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 2718625 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 91 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | 1.317 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 1643125 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 55 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 1.318 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 7289500 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 244 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 1.319 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 9769125 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 327, 161 within the plan period | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 1.32 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 5019000 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 168 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 1.321 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 4481250 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 150 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | 1.322 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 5437250 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 182 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 1.323 | Secondary Financial contributions | Financial contributions provided to deliver onsite secondary school | 01_Education | 01_Secondary | IDP modelling | Essential | 9739250 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 326 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
North Cotswold | North Cotswold Sub area | 1.324 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 6572500 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 220, including non-strategic sites | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs | To note sub area also includes consideration of Non-strategic allocations in sub area |  | Yes | Agreed in principle
South Cotswold | South Cotswold Sub area | 1.325 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 10396500 | GCC Education (Benchmark per Secondary pupil of £29,875 based on an estimated pupil yield of 348, including non-strategic sites | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs | To note sub area also includes consideration of Non-strategic allocations in sub area |  | Yes | Agreed in principle
District-wide | All sites | 1.41 | Post 16 education contribution | Contribution to strategic pot to support delivery of post 16 education | 01_Education | 01_Post 16 | IDP modelling | Important | 22645250 | GCC Education (Benchmark per post pupil of £29,875 for total of 758 places) | N/A | Section 106 | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
District-wide | All sites | 2.111 | Reinforcement of existing community space | Existing provision well served to be reinforced where required and for schemes which do not deliver their own community facilities. This could include improvement of service offer and installation of Community Public Access Defibrillators (CPADs) | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | Included in CIL | N/A | N/A | CIL | 07: Phased in line with delivery | Parish and Town Councils | Where strategic sites are identified to required the provision of new community facilities, they are encouraged to liaise with existing facilities to ensure alignment and collaboration where possible, including through combined facilities where appropriate |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 2.113 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. This will cover both local plan and beyond plan period growth scenario | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils | Cost estimate dependent on specification and subject to refinement. Broad order of magnitude costs provided to ensure considered at viability testing but subject to refinement at application stage. |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 2.114 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 500sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1500000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 2.115 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils | This is in excess of modelled need but considered to be the minimum viable size of amulti-functional community building and is otherwise required to support modelled mode share |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 2.116 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 600sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1800000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 2.117 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 600sqm to cover both the current Local Plan and the broad location for growth. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1800000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 2.118 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 2.119 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. At this stage this is considered to be the smallest viable community facility but subject to refinement at application stage | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | 2.12 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 2.121 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 600sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1800000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
District-wide | All sites | 2.21 | Reinforcement of existing Library provision to support current Local Plan growth | Current preferred option is the expansion/relocation of the Moreton-in- Marsh Library. The alternatives (a satellite site of collection point in a multifunctional community building) provides a pragmatic and sustainable alternatives, enabling access to core library services without the requirement for dedicated on-site staff at all times. Such facilities can deliver a meaningful library presence within new communities, supporting access to resources, digital inclusion, and reading engagement. Both options could offer a range of services, including (but not limited to): • A curated lending stock • Self-service kiosks for issuing and returning items • Book reservation and collection services • Public access computers • Printing and associated digital services These models offer flexibility in terms of location and design. Provision could be situated within a dedicated room or integrated into a shared community space, such as a hub, leisure facility, or café area | 02_Community and social infrastructure | 02_Library | IDP modelling | Important | 2970968 | GCC Developer Guide rate of £196 per homes x 15,158 homes | 0 | S106 | 07: Phased in line with delivery | GCC Libraries | Alternative sites for new sites will also be supported but subject to retention of existing staffing levels |  | Yes | Agreed in principle
Cirencester | All sites | 2.31 | Expansion of Stratton Cemetery | Potential expansion of Stratton Cemetery - provision of land in kind of CIL | 02_Community and social infrastructure | 02_Burial ground/cemeteries | CDC Bereavement team | Important | Included in CIL | Establishment costs are proportional to build out with largest barrier being the land transfer costs associated with adjacent land owner (BDL) | 0 | CIL | 05: 2033-2043 (inclusive) | CDC Bereavement team |  |  | No | Draft for comment
North Cotswold | North Cotswold Sub area | 3.11 | Land / contributions to support new GP surgery/ existing Business Case | Support Chipping Camden Surgery to be expanded to align with the current future funding commitment. In combination with schemes 3.11,3.12 and 3.13 these collectively provide circa 2,500sqm of practicing space capable of provide services to circa 30,000 patients though collective funding of approximately £18.24m). | 03_Primary Healthcare | 03_GP space | IDP modelling | Essential | Planning obligation/ covered by separate line item | N/A | Business case approved covering operational costs | S106/CIL | 01: 2027-2032 (inclusive) | GCC ICB; NHS | Cost assumed to be based on provision of land to support current business case approval and related to potential fallback mechanism contained in item 3.14 |  | Yes | Agreed in principle
Cirencester | Circencester Sub area | 3.12 | Land to support new GP surgery/ existing Business Cass | Support replacement of Pheonix Health surgery (moving from Chesterton Lane). In combination with schemes 3.11,3.12 and 3.13 these collectively provide circa 2,500sqm of practicing space capable of provide services to circa 30,000 patients though collective funding of approximately £18.24m). Currently envisaged to be delivered on existing Steadings site or as part of Southern Expansion through new build | 03_Primary Healthcare | 03_GP space | IDP modelling | Essential | Planning obligation/ covered by separate line item | N/A | Business case approved covering operational costs | S106/CIL | 01: 2027-2032 (inclusive) | GCC ICB; NHS | Cost assumed to be based on provision of land to support current business case approval and related to potential fallback mechanism contained in item 3.14 |  | Yes | Agreed in principle
Cirencester | Circencester Sub area | 3.13 | Identify land to support new GP surgery/ existing Business Cass | Support expansion of Cirencester Neighbourhood health centre In combination with schemes 3.11,3.12 and 3.13 these collectively provide circa 2,500sqm of practicing space capable of provide services to circa 30,000 patients though collective funding of approximately £18.24m). Specific site to be identified in Cirencester sub area, preliminarily identified as Land at Kingshill | 03_Primary Healthcare | 03_GP space | IDP modelling | Essential | Planning obligation/ covered by separate line item | N/A | Business case approved covering operational costs | S106/CIL | 01: 2027-2032 (inclusive) | GCC ICB; NHS | Cost assumed to be based on provision of land to support current business case approval and related to potential fallback mechanism contained in item 3.14. Alternative locations would also be considered on their merits but Kingshill benefits from the need for onsite facilities to support modal share and access to existing patient lists in Cirencester |  | Yes | Agreed in principle
District-wide | All sites | 3.14 | Residual need for primary healthcare (and consideration of fall back measures) | This scheme includes the residual cost estimate for additional planned projects towards the end of the Local Plan period, on the basis the identified schemes within this IDS collectively provide approximately 2,500sqm of practicing space. This cost would therefore mitigate the need for approximately 3,347 additional patients at the latter end of the plan period. This is currently understood to be reviewed at the Moreton-in-Marsh, subject to feasibility. | 03_Primary Healthcare | 03_GP space | IDP modelling | Important | 2034256 | Cost based on a plan wide need for 2,854sqm at a total costs of £20.26 million based on delivered and fitted out space, with provision for ceca 30,000 patients delivered by existing programme (at an equivalent new build cost of £18.24 million). The residual demand (3,347 patient or 287sqm) at the same fit out (£7,088 per sqm) is therefore included | See committed schemes | S106/CIL | 03: 2033-2037 (inclusive) | GCC ICB; NHS | As set out in the body of the IDP, whilst there is an element of funding committed as part of the business case under schemes 3.11,3.12 and 3.13, these are yet to be implemented. In this event, the same methodology would apply to the wider housing growth figures and therefore be increased significantly. As set out in the body of the IDP this would equate to an estimated range of £15.63 to £20.26 million. As a result if the on-site provision is not provided, off-site financial contribution towards refurb and/or extensions of impacted PCN(s). Any on-site provision should meet the NHS's minimum requirements regarding commercial terms, scale and design of the primary care facility |  | Yes
District-wide | All sites | 3.15 | Seek opportunities to provide a Neighbourhood Health Centre | Subject to business case work being prepared but the Neighbourhood Health Centre scheme is supported by CDC | 03_Primary Healthcare | 03_GP space | IDP modelling | Important | Included in CIL | N/A | N/A | CIL | 07: Phased in line with delivery | GCC ICB; NHS |  |  | No | Agreed in principle
District-wide | All sites | 4.11 | Compliance with onsite open space standards | Covering Accessible Green Space, Allotments and Play in particular | 04_Open space and Sports | 04_Onsite Open space standards | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 07: Phased in line with delivery | CDC Policy team; management companies | Costs considered covered by site delivery costs |  | No | Agreed in principle
District-wide | All sites | 4.21 | Sport hall CUAs | Support continued Community Use Agreements of sports halls, particularly in Cirencester and as part of new Educational facilities | 04_Open space and Sports | 04_Sport and recreation | Sport England | Important | Included in CIL | N/A | N/A | CIL | 04: 2038-2043 (inclusive) | Multi-academy trusts, CDC Leisure, Sports England, National Governing Boards |  |  | No | Agreed in principle
District-wide | All sites | 4.31 | KKP playing pitch report conclusions | Contributions to increase carrying capacity of existing facilities | 04_Open space and Sports | 04_Sport and recreation | KKP Playing Pitch Strategy | Important | Included in CIL | N/A | N/A | CIL | 07: Phased in line with delivery | CDC Leisure, Sports England, National Governing Boards |  |  | Yes | Draft for comment
District-wide | All sites | 4.32 | KKP playing pitch report conclusions | Local Plan wide need for 20 playing pitches (based on 0.65 pitches per 500 homes) | 04_Open space and Sports | 04_Sport and recreation | KKP Playing Pitch Strategy | Important | 3704707.6923 | KKP evidence base for pitch cost, calculated across plan period. This figure is based on capital costs only at this stage, and does not include ongoing lifecycle costs. These are dependent on the type of pitch provided and the management arrangement and will be subject to refinement at the application stage. | N/A | S106 | 07: Phased in line with delivery | CDC Leisure, Sports England, National Governing Boards, Strategic Sites | Scope of cost dependent on need identified at application stage. It is envisaged these will be delivered on the strategic sites in full although standalone sites will be supported |  | Yes | Draft for comment
District-wide | All sites | 4.33 | Lifecycle costs associated with pitch provision | Lifecycle costs associated with Local Plan wide need for 20 playing pitches | 04_Open space and Sports | 04_Sport and recreation | KKP Playing Pitch Strategy | Important | 3757000 | Lifecycle costs based on KKP estimate of £18,785 per annum for 10 years per site, combined with plan wide need for 20 pitches | N/A | S106 | 07: Phased in line with delivery | CDC Leisure, Sports England, National Governing Boards, Strategic Sites |  |  | Yes
District-wide | All sites | 4.34 | Indoor Sports Halls | Local Plan wide need for two new Sports Centres requiring 8 new courts. Given the distribution of unmet need across the district, the Council will seek provision via land at Strategic Sites and via financial contributions from all sites | 04_Open space and Sports | 04_Sport and recreation | AECOM Leisure addendum | Important | 5865436 | Sport England Facilities Calculator (utilising Q3 2025 build costs) | N/A | S106 | 07: Phased in line with delivery | CDC Leisure, Sports England, National Governing Boards, Strategic Sites |  |  | Yes
District-wide | All sites | 4.35 | Swimming pool provision | Local Plan wide need for the equivalent of 1.7 new swimming pools (calculated to be 358.16sqm or 6 lane equivalent). Given the distribution of unmet need across the district, the Council will seek provision (both land and proportional financial contributions) in both the North and South of the District | 04_Open space and Sports | 04_Sport and recreation | AECOM Leisure addendum | Important | 7736226 | Sport England Facilities Calculator (utilising Q3 2025 build costs) | N/A | S106 | 07: Phased in line with delivery | CDC Leisure, Sports England, National Governing Boards, Strategic Sites |  |  | Yes
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 4.41 | Onsite SANG | The provision of onsite SANG (delivered in line with Natural England Guidance) based on the need to provide 8ha per 1000 people. Suitable offsite solutions which mitigate the same impact will also be considered on its merits. | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | Planning obligation | N/A | N/A | Direct delivery | 01: 2027-2032 (inclusive) | Natural England | Considered covered by site delivery costs |  | Yes | Agreed in principle
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 4.42 | Onsite ANRG | The provision of onsite ANRG (delivered in line with Natural England Guidance). Suitable offsite solutions which mitigate the same impact will also be considered on its merits. | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | Planning obligation | N/A | 0 | Direct delivery | 01: 2027-2032 (inclusive) | Natural England | Considered covered by site delivery costs |  | Yes | Agreed in principle
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 4.43 | Onsite ANRG | The provision of onsite ANRG (delivered in line with Natural England Guidance). Suitable offsite solutions which mitigate the same impact will also be considered on its merits. | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | Planning obligation | N/A | N/A | Direct delivery | 01: 2027-2032 (inclusive) | Natural England | Considered covered by site delivery costs |  | Yes | Agreed in principle
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 4.44 | Onsite SANG | The provision of onsite SANG (delivered in line with Natural England Guidance) based on the need to provide 8ha per 1000 people. Suitable offsite solutions which mitigate the same impact will also be considered on its merits. | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | Planning obligation | N/A | N/A | Direct delivery | 01: 2027-2032 (inclusive) | Natural England | Considered covered by site delivery costs |  | Yes | Agreed in principle
District-wide | All sites | 4.45 | Strategic Local Plan SANG to serve non-strategic and windfall sites | Potential need for residual SANG provision to mitigate impact of windfall, saved allocations and non-strategic allocations of circa 15ha, subject to scale of windfall development. Could be provided as part of strategic sites, or an alterative potential strategic location for Local Plan SANG. This has preliminarily been identified adjacent to the Kemble Strategic Site but would be paid for by qualifying development | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 0 | Potential to be delivered as a commercial enterprise | N/A | Direct delivery | 01: 2027-2032 (inclusive) | Natural England; CDC | Alternative sites will also be supported. Please see policy position. SANG Strategy estimates that the total per hectare cost for the creation of an appropriate SANG site has been calculated to be £17,615.64. |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 4.46 | North Meadow SAMM contribution | Contributions to North Meadows SAMM mitigation to provide onsite enhancements in line with latest recreation mitigation strategy | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 218356.73 | SAMM tariffs taken from CDC website (April 2026) of £356.21 per dwelling for North Meadow | N/A | S106 | 07: Phased in line with delivery | Natural England; CDC |  |  | Yes | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 4.46 | North Meadow SAMM contribution | Contributions to North Meadows SAMM mitigation to provide onsite enhancements in line with latest recreation mitigation strategy | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 406435.61 | SAMM tariffs taken from CDC website (April 2026) of £356.21 per dwelling for North Meadow | N/A | S106 | 07: Phased in line with delivery | Natural England; CDC |  |  | Yes | Draft for comment
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 4.46 | North Meadow SAMM contribution | Contributions to North Meadows SAMM mitigation to provide onsite enhancements in line with latest recreation mitigation strategy | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 487295.28 | SAMM tariffs taken from CDC website (April 2026) of £356.21 per dwelling for North Meadow | N/A | S106 | 07: Phased in line with delivery | Natural England; CDC |  |  | Yes | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 4.46 | North Meadow SAMM contribution | Contributions to North Meadows SAMM mitigation to provide onsite enhancements in line with latest recreation mitigation strategy | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 791498.62 | SAMM tariffs taken from CDC website (April 2026) of £356.21 per dwelling for North Meadow | N/A | S106 | 07: Phased in line with delivery | Natural England; CDC |  |  | Yes | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | 4.46 | North Meadow SAMM contribution | Contributions to North Meadows SAMM mitigation to provide onsite enhancements in line with latest recreation mitigation strategy | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 132510.12 | SAMM tariffs taken from CDC website (April 2026) of £356.21 per dwelling for North Meadow | N/A | S106 | 07: Phased in line with delivery | Natural England; CDC |  |  | Yes | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 4.46 | Beechwood SAMM contribution | Contributions to Beechwood SAMM mitigation to provide onsite enhancements in line with latest recreation mitigation strategy | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 225756.6 | SAMM tariffs taken from CDC website (April 2026) of £221.33 per dwelling | N/A | S106 | 07: Phased in line with delivery | Natural England; CDC |  |  | Yes | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 4.46 | North Meadow SAMM contribution | Contributions to North Meadows SAMM mitigation to provide onsite enhancements in line with latest recreation mitigation strategy | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 590596.18 | SAMM tariffs taken from CDC website (April 2026) of £356.21 per dwelling for North Meadow | N/A | S106 | 07: Phased in line with delivery | Natural England; CDC |  |  | Yes | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 4.46 | North Meadow and Beechwood SAMM contribution | Contributions to North Meadows and Beechwood SAMM mitigation to provide onsite enhancements in line with latest recreation mitigation strategy | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 787764.56 | SAMM tariffs taken from CDC website (April 2026) of £221.33 per dwelling for Beechwoods and £356.21 per dwelling for North Meadow | N/A | S106 | 07: Phased in line with delivery | Natural England; CDC |  |  | Yes | Draft for comment
South Cotswold | South Cotswold Sub area | 4.46 | North Meadow and Beechwood SAMM contribution | Residual contributions to North Meadows and Beechwood SAMM mitigation to provide onsite enhancements in line with latest recreation mitigation strategy for non strategic allocations and estimated windfall | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 1014295.57 | SAMM tariffs taken from CDC website (April 2026) of £221.33 per dwelling for Beechwoods and £356.21 per dwelling for North Meadow | N/A | S106 | 07: Phased in line with delivery | Natural England; CDC | To note that the detailed contribution due will be calculated per dwelling at the application stage |  | Yes | Draft for comment
District-wide | All sites | 6.11 | Fibre to the premises | FTTP expectation for all schemes over 10 homes | 06_Utilities | 06_Digital | GCC developer guide | Important | Planning obligation | N/A | Full costs | Likely funded by Universal Service Obligation | 07: Phased in line with delivery | Openreach |  |  | No | Agreed in principle
District-wide | All sites | 6.21 | Reinforcement of electricity supply | Scale of reinforcement dependent on wider energy transition. Requirements likely to be triggered in early stages of the local plan (0-5 years) and therefore early engagement is required to determine scale of upgrade required once Local Plan is found sound. Specific schemes identified as supporting scale of growth identified separately | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 01: 2027-2032 (inclusive) | SSEN |  |  | No | Draft for comment
District-wide | Circencester Sub area | 6.22 | Reinforcement of electricity supply | CIRENCESTER Bulk Supply Point (Earliest identified negative headroom [minimum headroom scenario] in future projection occurs in 2031) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 01: 2027-2032 (inclusive) | SSEN |  | To be refined with statutory providers | No | Draft for comment
District-wide | All sites | 6.23 | Reinforcement of electricity supply | STRATTON (RESERVE) Bulk Supply Point (Earliest identified negative headroom [minimum headroom scenario] in future projection occurs in 2029) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 01: 2027-2032 (inclusive) | SSEN |  | To be refined with statutory providers | No | Draft for comment
District-wide | South Cotswold Sub area | 6.24 | Reinforcement of electricity supply | MELKSHAM Grid Supply point (Earliest in service date for applications >1MW in 2036) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 03: 2033-2037 (inclusive) | SSEN | To note it is estimated that the Melksham GSP currently serves nearly 250,000 customers and is in the process of being upgraded | To be refined with statutory providers | No | Draft for comment
District-wide | North Cotswold Sub area | 6.25 | Reinforcement of electricity supply | COWLEY Grid Supply point (Earliest in service date for applications >1MW in 2029) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 01: 2027-2032 (inclusive) | SSEN | To note it is estimated that the Cowley GSP currently serves nearly 270,000 customers and is in the process of being upgraded | To be refined with statutory providers | No | Draft for comment
District-wide | All sites | 6.26 | Reinforcement of electricity supply | Minety Grid Supply point (Earliest in service date for applications >1MW in 2036) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 02: 2027-2037 (inclusive) | SSEN | To note it is estimated that the Minety GSP currently serves nearly 150,000 customers and is in the process of being upgraded | To be refined with statutory providers | No | Draft for comment
North Cotswold | North Cotswold Sub area | 6.27 | Reinforcement of electricity supply | Moreton-in-Marsh Primary substation | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 02: 2027-2037 (inclusive) | National Grid/Western Power Distribution |  | To be refined with statutory providers | No | Draft for comment
Cirencester | Circencester Sub area | 6.31 | Cirencester STW | Cirencester - Will be approaching its permit limit towards the end of the plan period and would only have 5% headroom left in 2045. As a result, it will likely require planned upgrades within the plan period | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Critical | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 06: 2027-2043 (inclusive) | Thames water |  | To be refined with statutory providers | No | Draft for comment
Fairford | Fairford Sub area | 6.32 | Fairford STW works | Fairford - Expected to require additional capacity between 2030 and 2035 | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 01: 2027-2032 (inclusive) | Thames water |  | To be refined with statutory providers | No | Draft for comment
Mickleton | Mickleton Sub area | 6.33 | Honeybourne STW | Honeybourne - Expected to require additional capacity between 2040 and 2045 | 06_Utilities | 06_Water Supply and Wastewater | Severn Trent | Critical | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 04: 2038-2043 (inclusive) | Severn Trent |  | To be refined with statutory providers | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh Sub area | 6.34 | Moreton in Marsh STW | Moreton-in-Marsh - Expected to require additional capacity between 2030 and 2035 | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Critical | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 01: 2027-2032 (inclusive) | Thames water |  | To be refined with statutory providers | No | Draft for comment
North Cotswold | North Cotswold Sub area | 6.35 | Blockley STW | Blockley STW is currently at or close to capacity and could impact windfall development | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 01: 2027-2032 (inclusive) | Thames water |  | To be refined with statutory providers | No | Draft for comment
South Cotswold | Multiple: Ampney St Peter STW | 6.36 | Ampney St Peter | Ampney St Peter - Expected to require additional capacity between 2030 and 2035 | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 01: 2027-2032 (inclusive) | Thames water |  | To be refined with statutory providers | No | Draft for comment
South Cotswold | South Cotswold Sub area | 6.37 | Lechlade STW | Lechlade - Will be approaching its permit limit towards the end of the plan period and would only have 7% headroom left in 2045. As a result, it will likely require planned upgrades within the plan period | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 04: 2038-2043 (inclusive) | Thames water |  | To be refined with statutory providers | No | Draft for comment
Kemble | Kemble Sub area | 6.38 | Wessex Water upgrades | Given scale of growth envisaged within their coverage area, no mitigation was identified as required to serve the additional growth although this is dependent on the scale of windfall growth and is therefore added to this IDS for completeness. | 06_Utilities | 06_Water Supply and Wastewater | Wessex Water | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 04: 2038-2043 (inclusive) | Wessex Water |  |  | No
Kemble | Kemble Sub area | 6.39 | Bristol Water upgrades | Given scale of growth envisaged within their coverage area, no mitigation was identified as required to serve the additional growth although this is dependent on the scale of windfall growth and is therefore added to this IDS for completeness. | 06_Utilities | 06_Water Supply and Wastewater | Bristol Water | Essential | 0 | N/a | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 04: 2038-2043 (inclusive) | Bristol Water |  |  | No
District-wide | All sites | 7.11 | Consolidation of blue light facilities | Support in the delivery of shared services and hubs and in existing Community Fire Stations, in line with the GFRS 'Productivity and Efficiency Plan 2025-2026' | 07_Emergency services | 07_Fire and rescue | IDP modelling | Important | Included in CIL | N/A | CIL | S106; CIL; National funding | 07: Phased in line with delivery | Gloucestershire Constabulary; SW Ambulance Service; Gloucestershire Fire and Rescue | Identified through a number of strategic plans but not specific project identified as required to deliver the local plan growth |  | No | Draft for comment
District-wide | All sites | 7.12 | Support for consolidation of existing facilities and inclusion within multi-functional community hubs for blue light functions | Support in the delivery of shared services and hubs within new proposed community hubs provided on strategic sites | 07_Emergency services | 07_Police | IDP modelling | Important | Covered separately under multifunctional community hub costs | N/A | N/A | S106; CIL; National funding | 07: Phased in line with delivery | Gloucestershire Constabulary; SW Ambulance Service; Gloucestershire Fire and Rescue | Costs included in estimates for multifunctional community building |  | No | Draft for comment
District-wide | All sites | 7.21 | On site provision of hydrants | Requirement for on site hydrant provision for schemes over 50 homes and on selected commercial developments. Where local fire risk could be demonstrably heightened, the provision for modern suppression in appropriate homes to reduce call outs will be sought | 07_Emergency services | 07_Fire and rescue | GCC developer guide | Important | Planning obligation | N/A | N/A | Direct delivery | 07: Phased in line with delivery | Gloucestershire Fire and Rescue | Scale of obligation considered to be covered by site development costs |  | No | Agreed in principle
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 7.31 | New Community Response post | Provision of space within strategic site applications to allow for parking of response vehicles, ideally adjacent to usable facilities within community hubs | 07_Emergency services | 07_Ambulance | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 02: 2027-2037 (inclusive) | SW Ambulance Trust | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 7.32 | New Community Response post | Provision of space within strategic site applications to allow for parking of response vehicles, ideally adjacent to usable facilities within community hubs | 07_Emergency services | 07_Ambulance | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 02: 2027-2037 (inclusive) | SW Ambulance Trust | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 7.33 | New Community Response post | Provision of space within strategic site applications to allow for parking of response vehicles, ideally adjacent to usable facilities within community hubs | 07_Emergency services | 07_Ambulance | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 02: 2027-2037 (inclusive) | SW Ambulance Trust | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 7.34 | New Community Response post | Provision of space within strategic site applications to allow for parking of response vehicles, ideally adjacent to usable facilities within community hubs | 07_Emergency services | 07_Ambulance | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 02: 2027-2037 (inclusive) | SW Ambulance Trust | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
District-wide | All sites | 8.11 | On site SUDS | To meet local plan standards | 08_Flood Management | 08_Onsite mitigation | SFRA | Essential | Planning obligation | N/A | N/A | Direct delivery | 07: Phased in line with delivery | Strategic site promoter | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
Cirencester | Circencester Sub area | 8.12 | Natural Flood Mitigation schemes | CDC support for GCC programme of work for natural flood mitigation at the parish level | 08_Flood Management | 08_Offsite mitigation | LLFA | Important | Included in CIL | N/A | 0 | S106; CIL; EA | 04: 2038-2043 (inclusive) | GCC LLFA |  | To check if still appetite to support at CDC and GCC- retained from previous IDP | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa14 | Fairford-Circencester AT Route | An active travel route including cycling and walking to join onto intervention D7 to provide a route between all the major sites and Cirencester. This route is 10.7km long and would be formed through 3.4km predominantly upgraded bridleways, footpaths and tracks followed by 1.3km of quiet lane treatment followed by 1.6km of on road segregation followed by 3.2km of quiet lane treatment on Welsh Way followed by small bit of shared pathway on the A417 between Village Street and Waterton Farm (BAC25 footpath) 0.4km followed by 1.7km of upgraded footpath to shared space. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 5000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir10 | Siddington Road Cycleway | Provision of an on-road cycleway connecting Sites SD23 and SD17 to town centre via Siddington Road. Cycleway would follow Siddington Road then turn onto Kingsmead Road to connect to existing cycleway underpass under Bristol Road. To be delivered along with Cir5 to provide onwards cycle access to town centre. | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 300000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir11 | Extend London Road cycleway | Extend London Road cycleway next to Site C81B toward town centre with on-road cycle lane. Connect to existing active travel bridge over Swindon Road, creating a shared use path for pedestrians and cyclists. Rejoin cycleway to London Road and towards town centre with | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Kemble Sub area | Cir12 | Enhancement to 882 bus service | Increase the frequency of the Stagecoach West 882 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 01: 2027-2032 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir14 | Cirencester mobility hub | Development of a new or enhanced mobility hub integrating public transport, micromobility, cycle facilities, and shared mobility options | 05_Transport | 05_Supporting Sustainable transport integration | Cotswold DC | Essential | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | All sites | Cir15 | Cirencester Park and Ride | Park and ride/stride provision to intercept car trips at the edge of town, with potential for targeted bus priority measures to improve reliability and attractiveness of services into Cirencester. Park and Rides tend to target cars coming from out of town. Given the placement of this it is unlikely to be used by sites within the local plan. It is will be important for reducing overall traffic levels which may help local plan traffic however at present the modelling does not suggest it is critical for the functioning of the network | 05_Transport | 05_Public transport - Bus | Cotswold DC | Important | 10000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 04: 2038-2043 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir16 | Wayfinding improvements | Introduction of a coherent, high-quality wayfinding strategy to improve navigation, reinforce key destinations, and enhance the legibility of walking and cycling networks across the town. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Important | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 05: 2033-2043 (inclusive) | GCC; Town and Parish Councils |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir17 | East-West Pedestrian / Cycle route improvements | Strengthening east–west pedestrian and cycle connectivity across Cirencester, improving continuity, safety, and accessibility. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Important | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir18 | Tesco–Siddington Road Active Travel Link | Creation of a direct, safe walking and cycling route connecting Tesco to Siddington Road, improving local accessibility and reducing short car trips. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Essential | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 05: 2033-2043 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir19 | Orchard Fields–Steadings Active Link | Establishment of a walking and cycling route through Orchard Fields connecting Siddington to The Steadings. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Essential | 375000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 05: 2033-2043 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir2 | Spratsgate Lane/Somerfield Road active travel links | Package of active travel measure could include providing pedestrian footpaths for residents willing to walk into Cirencester, as well as a on-road segregated cycleway. Require active travel access points along Spratsgate Lane for Sites SD20 and C190 | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir20 | Siddington–South Cerney active travel link | Development of a strategic active travel corridor utilising the disused railway line to provide a direct, segregated walking and cycling link between Siddington and South Cerney. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Essential | 1100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir21 | Green Lane Quiet Road | Reclassification of Green Lane (off Clark’s Lane) from highway use to a quiet lane with lower speed limits and appropriate signage to enable shared use road for walking and cycling. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Essential | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir22 | A417 Underpass Roundabouts Active Travel Mitigation | Model suggests that cycling along the Dower's Lane becomes unsuitable for most people from suitable for some people due to increased traffic volumes. Many surrounding roads are currently assessed to have low suitability for cycling however there are a few off-road routes nearby meaning some cycle routing may be happening. Mitigation is likely to involve speed limit treatment on Dower's Lane and a shared pathway/cyclops upgrade to the two roundabouts. There is limited suitability in the wider area for cycling so this is unlikely to be a critical mitigation | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir23 | Spratsgate Lane AT Mitigation | At present the road has minimal segregated infrastructure (with the exception of the new roundabout that feeds into the development near the Wilkinson Road Junction). The change is traffic is significant enough that even with minimal interventions such as 20mph zones and traffic calming or non-segregated cycle lanes are unlikely to be sufficient to leave the road suitable for most people. At present this route lies on the National Route 45. Multiple options should be explored including providing segregated provision or through alternative routing for the key routes that may use this route. For example K10 intervention may open up a route through Chesterton Farm and into the town centre and to east provision could be improved for a route along love lane. These interventions would be in addition to that proposed as part of the committed steadings site. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir24 | On site provision of services | Site further from Cirencester Town centre require on site provision of essential services to reduce travel in to the town centre. This should include at a minimum a primary school, a community space, a retail offering (ideally a small convenience store and service for last mile delivery such a RM parcel box and parcel collection (either within a retail offering or through an external parcel collection service). | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir25 | Kingshill Road/London Road mitigation | Upgrade Junction to a signalised Junction​ | 05_Transport | 05_Highways | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir26 | Kingshill Road/Cirencester Road mitigation | Upgrade Junction to a signalised Junction​ | 05_Transport | 05_Highways | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir27 | Somerford Road/Chesterton Lane HW Mitigation | Upgrade intersection between Somerford road and Chesterton lane to be signalised. The modelling suggests that increased traffic on Chesterton road will lead to severe queueing on the Somerford road due to them being unable to merge | 05_Transport | 05_Highways | City Science modelling | Essential | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir28 | Cirencester Road AT Flag | Limit issues for active travel using speed limits (20mph) and soft segregation | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 |  | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir29​ | B4425/A429 Stow Road mitigation ​ | Signal Optimisation/ Increase cycle time (reduce amount of loss time for Cherrytree Ln and increase green time B4425 and Stow Rd)​ Required to deal with harm to network​ | 05_Transport | 05_Highways | City Science modelling | Critical | 50000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir3 | Active travel access Swindon Road | Active travel access onto Swindon Road at the northeastern corner of Site R519 to give access to existing cycleway crossing the A419 and along Cricklade Road to town centre. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 200000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir30 | Cirencester-Swindon BRT | Implementation of BRT route prosed between Cirencester and Swindon. This is assumed to contain enough bus priority interventions to keep the journey times down and a service that is frequent a minimum of every fifteen minutes. In order to maximise the utility of these route for the local plan it is assumed that this will be an express stopping service that would call at Swindon-Down Ampney-Driffield Junction- Preston-Kingshill Lane-Cirencester. This captures around 2300 dwellings in the local plan. Journey time between Swindon and Cirencester should be no longer than 50-60 minutes to provide a competitive journey time to driving. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 5000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir32 | Enhanced or extended bus service between Site C187 via the Steadings to Cirencester | Increase the frequency of existing bus routes or implementation of a new bus route to connect the new site south of the Steadings via The Steadings to Cirencester. Could include a bus gate to permit bus movements between the Steadings and site C187. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC | Scheme requires alignment between saved allocation and Steadings Phase 2 |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir33 | Local transport corridor interchange hub in The Steadings | Implement a Local Transport Corridor Interchange Hub within The Steadings where bus service between The Steading and Cirencester will stop on site. | 05_Transport | 05_Supporting Sustainable transport integration | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 1000000 | S106 | 01: 2027-2032 (inclusive) | Bathurst Development Ltd; GCC | Existing scheme being delivered by the Steading existing allocation and included as an assumption in the baseline transport modelling |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir34 | 20mph zones | Extended the 20mph zones to cover residential street and development sites. This follows the consultation currently out | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Essential | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir35 | Active Travel Route from South Steadings to Tetbury Road Entrance of Agricultural College | Route following the existing planned interconnection between the Steadings and South Steadings extension. Exiting on the southern access from the Steadings (assuming the roundabout has been designed with adequate segregation. Then 0.2km of shared pathway on the north bound side of the road. Given the likely low volumes of both pedestrians and cyclists a 3m shared pathway would be sufficient and can be delivered within the HW boundary | 05_Transport | 05_Active travel / public realm | City Science/ GCC | Critical | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC; Agricultural College |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir36​ | A419 Swindon Road/Silver Street | Upgrade the junction to a signalised junction and add approach flares. | 05_Transport | 05_Highways | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir37 | A429/Chesterton Ln Junction​ | Change the stages and phases (having an all A429 stage followed by a Chesterton ln stage, and more green time for Stroud lane approach) ​ | 05_Transport | 05_Highways | City Science modelling | Critical | 50000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | Cir38 | A419 Stroud Road/Trewsbury Road | Upgrade the junction to a signalised junction and add approach flares. | 05_Transport | 05_Highways | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir39 | A429 Watermoor Roundabout | Add approach arm flares to the roundabout and widen the eastbound approach arm. | 05_Transport | 05_Highways | City Science modelling | Critical | 10000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir4 | Cricklade Road Cycleway Enhancement | Upgrade the cycleway from Preston Toll Bar along Cricklade Road by installing high-quality road surface throughout, introducing a designated on-road cycle lane, and implementing clear signage. Extend this cycleway improvements to the town centre, passing under the foot tunnel under the Bristol Road and joining Watermoor Way | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir40 | Stroud Road north of Tetbury Roundabout | Widen the road to two lanes to accommodate development access. | 05_Transport | 05_Highways | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways | Existing scheme being delivered by the Steading existing allocation and included as an assumption in the baseline transport modelling |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir41 | A419 Swindon Road\Cirencester Road | Widen the roundabout to provide two lanes between the roundabout and the Kingsmill Lane signalised junction. | 05_Transport | 05_Highways | City Science modelling | Critical | 10000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir42 | A29 Swindon Road/Bristol Road Roundabout | Widen the roundabout. | 05_Transport | 05_Highways | City Science modelling | Critical | 10000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir43 | Chesterton Road Active Travel Mitigation | Segregated cycle route from Chesterton Farm Lodge to join into A429/A419 underpass. This is to account for the decreased suitability for mixed traffic cycling due to the increase in traffic. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 300000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 07: Phased in line with delivery | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir5 | Watermoor Road space reallocation | Reallocate road space along Watermoor Road to create a serrated cycleway, joining with Cycleway improvements in Cir4 to provide active travel links for southern development sites into Cirencester. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir7 | Active travel access on Kingshill Lane | Active travel access on western boundary of site directly opposite off road leading to Cirencester skate park. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir8 | Queen Elizabeth Road/Beeches Road cycleway | On road cycleway connecting to existing east-west cycle route to link Sites R650 and R519 to town centre. Include on road cycleways along Queen Elizabeth Road and Beeches Road. Then a segregated cycle lane along London Road/Lewis Lane to access town centre. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir9 | Pedestrianise Castle Street | Extend current pedestrian zone restrictions to on Crickade Road to cover Castle Street for more attractive placemaking in town centre. Reallocate road space to active travel infrastructure and green space. Divert East West traffic along Park Lane, Black Jack Street, Market Place and The Waterloo to reach London Road | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC; Town and Parish Councils |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D1 | On site provision of services | Site requires on-Site provision of key services such as retail and healthcare as there is currently only one small village shop in Down Ampney, with other retail and healthcare services located over 3km away. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D2 | Cricklade cycle route | Cycleway connecting Down Ampney and Cricklade to give sustainable access to retail services in Crickade. Route would follow Down Ampney Road and head south on Cirencester road, cross the A419 and continue down into Crickade. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 900000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D3 | South Cerney cycle route | Cycleway connecting Down Ampney and Cricklade to give sustainable access to retail services in South Cerney. Route would follow Down Ampney Road west and cross the A419, before turning north onto Cerney Wick Lane and following north on to Station Road into the centre of South Cerney. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1750000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D6 | Enhancements of 76 bus route | Increase the frequency of the Stagecoach West 76 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D7 | Down Ampney -Cirencester Greenway | Extended greenway linking Sites in Down Ampney to Cirencester. Route would extend up through the sites in Down Ampney, north along the PROW route (BDA1) and the west towards Driffield (Route BDD16). It would then connect with the sites at Driffield Junction Development, running directly through these sites and onwards to the existing bridleway running northeast from Harnhill and adjacent to the A419. It would cross the A417 at Witpit Lane and connect to the sites along Kingshill Lane. For there it would follow Cir8 into town centre. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Critical | 3500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D9 | 20mph zones | Introducing 20mph zones across Down Ampney including within development sites | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Essential | 75000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | Direct delivery | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D10 | Quiet Lane Treatment on Unnamed Road between Oak Road and Fairford Road | In order to limit the use of this not suitable single track road several measures are pursued: Speed limit Change from National Speed limit to 30mph - this change will ensure that subtility level for active travel is improved as well as limit the perceived advantage of the route. Traffic calming measures including road marking and bumps. In addition formally designating this as a rural quiet lane with measures to ensure that traffic is kept beneath 1000 pcu a day. Finally in order to facilitated passing more passing places to be implemented with | 05_Transport | 05_Highways | City Science modelling | Essential | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ1 | On site provision of services | Site requires on-Site provision of key services such as retail, education and healthcare as closest services are 2 miles away in South Cerney or Down Ampney. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ10​ | B4696 Spine Rd Approach to Station Rd/Cerney Wick Ln Intersection​ | Upgrade Junction to a signalised Junction​ | 05_Transport | 05_Highways | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ2 | South Cerney active travel route | Provision of a segregated cycleway linking the western boundary of the Site to services in South Cerney for those who are able to cycle the distance. This could include active travel priority at A419/B4696 junction, then an onwards active travel route along the B4696 and Station Road into South Cerney. Alternatively could explore an active travel bridge over A419 connecting to and active trave route along Bow Wow Road directly into South Cerney. This assumed D3 is delivered | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 200000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ3 | Cirencester active travel route | Provision of a segregated cycleway connecting the Site to Cirencester via Cirencester Road for those able to cycle the distance. It is assumed that this should be delivered using a crossing of Cirencester Road which requires a change in the character of that road. GCC expressed support for this. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 5000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ5 | Driffield Junction Development Village Mobility Hub | A smaller mobility hub providing bus services, EV charging and parcel drop off points. | 05_Transport | 05_Supporting Sustainable transport integration | City Science modelling | Critical | 1500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ8 | Bridleway enhancement to Down Ampney (Wiltshire) | Enhancement of Bridleways through Wiltshire to high quality cycleway and walking route to Down Ampney | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 750000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | Wilshire Highways | To note this scheme would be implemented outside of GCC highways boundary in Wiltshire |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa1 | On site provision of services | On-Site provision of key services such as retail and healthcare. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa10 | Enhancement to 76 bus service | Increase the frequency of the Stagecoach West 76 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 350000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Fairford | Fairford Sub area | Fa11 | Fairford High Street Placemaking and AT | Increased traffic from Local Plan developments lead the high street to become "unsuitable" for most people. At present the high street has dedicated a lot of space to private vehicle use including parking and minimal space to active travel. Possible solutions include limiting or removing through traffic from the high street, full pedestrianisation, a one way system in additional to the removal of parking to allow for more segregated routes. | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa12 | 20mph zones | Introducing 20mph zones across Down Ampney including within development sites | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa13 | Fairford-Lechlade AT Route | Segregated Cycleway on Park Street (0.3km) followed by quiet lane treatment (with physical calming measures) on Leafield Road (0.5km) followed by footway upgrade to shared space (0.4km), segregated route along Hatherop Lane (0.3km) and then again (shared) along to Slothop Road (2.2km) followed by enhanced of a bridleway (1.6km) finally quiet lane treatment on Hambidge Lane (2.7km). Cost is additional to Fa3. This scheme is dependent on Fa2 being delivered | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 800000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa2 | Southrop Road/London Road active travel route | Provision of a segregated active route linking Site F57C to the town centre via Southrop Road and London Road. Package of measures include ensuring filling in gaps in pedestrian infrastructure and ensuring continuous footpaths and adequate crossing facilities, as well as enabling a shared used road with a cycleway. Requires active travel access of the southern boundary of the large Site along Hatherop Road and active travel access of the northern boundary of the large Site south of Southrop road. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa3 | Hatherop Road active travel route | Provision of an active route connecting Site F57B to the town centre via Hatherop Road. Measures could include widening existing footpaths in some areas and, ensuing adequate crossing facilities and implementing shared used road with a cycleway. Requires active travel access to Site along northwestern boundary along Hatherop Road. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa5 | Cinder Lane quiet road | Designation of Cinder Lane as a quiet road, to encourage active travel from Site F20A to the Town centre. Requires active travel access to Cinder Lane on northern boundary of Site. Includes surfacing upgrade. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 380000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa6 | Horcott Road active travel route | Improve active travel links along Horcott Road to encourage sustainable access from Site F53A to the town centre. This includes by widen footpaths and improving crossing over wide-mouth junctions heading to town centre, as well as introducing a cycleway. This could connect to existing the cycleway crossing Dilly's Bridge and connecting to Gas Lane, providing a more direct route to High Street. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 620000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa8 | Leafield Road Crossing | Provision of pedestrian crossing connecting Site to the east of Leafield Road to the Primary School opposite. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 140000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | Multi-academy trust; GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa9 | Leafield Road active travel route | Providing footpaths along Leafield road and a cycleway to enable active travel into town centre from Site F57A. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K10 | Kemble -Cirencester cycleway | Reuse of former rail route as a cycleway connecting Kemble and Cirencester for access to employment and education. | 05_Transport | 05_Active travel / public realm | GCC (LTP) | Critical | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K12 | Kemble to Tetbury Service bus service | New bus service connecting town centre of Kemble, developments Sites and Tetbury, along A439, Oxleaze Road and A433. Modelling suggests 100-200 passengers a day | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K13 | On site provision of services | Sites require on-site provision of key services such as retail and healthcare as there are minimal key services available in Kemble. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K14 | Windmill Road AT Mitigation | Flag identifies cycling may become unsuitable for most people as a result of increased traffic flow. At present the road is functionally not a full two-way street due to parking on the street. Mitigation could involve removing on street parking given most houses have drives to accommodate segregation | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 160000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K15 | Kemble to Ewen Cycle Mitigation | Model suggests that local plan traffic will make Windmill Road, School Road to Ewen no longer 'suitable for most people'. Mitigation involves shared pathway and reduction to 40mph | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 1100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K20 | 20mph zones | Introducing 20mph zones across all streets in Kemble, including within the development sites. | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K3 | Church Road active travel | Improvements to active travel along Church Road for Site K12. This includes active travel access to site boundary on Church road, continuous footways and possible exploration of a quiet lane on Church Road with lower speed limits and signage to improve mixed use of road for cycling. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K5 | Improved A429 crossing facilities | Improved active travel crossing facilities to allow active travel access from Site K12 to access Station Road, for onwards access to Kemble Station. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K6 | Station Road active travel | Improved pedestrian footways and cycleways along Station Road to promote active travel access from Sites K12 to Kemble Station | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 120000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K8 | Kemble station improvements | Package of improvements including improving accessibility at the station with step free bridge, cycle parking etc. | 05_Transport | 05_Public transport - Rail | GCC (LTP) | Critical | 2500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | GWR, Network Rail |  |  | No | Draft for comment
Kemble | Kemble Sub area | K21 | Anti-Ratrunning Measures on Unnamed Road between A429 and A433 | Minor alterations including speed interventions and no left turn into it from A429 and no right turn into it from A433 in order to stop traffic using to avoid A429/A433 junction | 05_Transport | 05_Highways | City Science modelling | Critical | 10000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | LP10 | B4040/B4696 | Signal Optimisation | 05_Transport | 05_Highways | City Science modelling | Essential | 50000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | Wilshire Highways | To note this scheme would be implemented outside of GCC highways boundary in Wiltshire |  | No | Draft for comment
Kemble | North Cotswold Sub area | LP7​ | Stow-on-the-Wold Sheep Street/A429/High Street Mitigation​ | Change signal stages with indicative arrows at high street/Roman Rd Junctions.​ Signal optimisation at A429/B4068. | 05_Transport | 05_Highways | City Science modelling | Critical | 130000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | LP8 | Avening High Street AT Mitigation | Model suggests that Avening High Street becomes unsuitable to most people to cycle on after the local plan. Mixed traffic suitability could be restored if the speed limit is reduced to 20mph with a corresponding amount of traffic calming to ensure the design speed matches the new speed limit. The remainder of links surrounding this one are deemed unsuitable according to LTN1/20 before and after the local plan which means this stretch is unlikely to currently form part of a whole route however there are some non-road routes near by which this may cut off. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | LP9 | Coates AT Mitigation | Model suggests that cycling on the Trewsbury Road becomes unsuitable for most people due to increased traffic volumes. Caveat: At present all the surrounding rounds into Coates are current deemed to be unsuitable for most cyclists and this is unlikely to block a route. Solutions include implementing a one way system around coates to allow for cycle lanes and/or speed reductions. | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | North Cotswold Sub area | LP16 | Willersey AT Flag | Willersey Leamington Road and Main Street because unsuitable for cycling due to increased traffic. 20mph speed limit would resolve this. | 05_Transport | 05_Highways | City Science modelling | Critical | 10000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic11 | 20mph zones | Introducing 20mph zones across all streets in Mickleton, including within the development sites. | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic2 | Site Active Travel Connections and wider offsite improvements to car-free routes | Active Travel only connections to the public park to provide attractive active travel routes within Mickleton. At present the paths within the park are not sufficient for cycling and so upgrade of widths for a shared pathway or separate cycling routes would be required. Includes at least 2.6km of pathways to upgrade | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic3 | Long Marsdon Road Active Travel Connection | Cycleway and/or Shared Pathways along Long Marsdon Road to facilitate segregated access to National Cycleway 5 route featuring a fully car-free travel route to Stratford-Upon-Avon the distance being approximated 12-14km/ 7.5-8.5 mi within the distance that some may commute especially if coupled with targeted e-micromobility interventions. | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | 3500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic5 | On site provision of services | At present that are limited services within Mickleton itself. Providing a local hub including some GP services, Schools and Retail offerings and mobility hub | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic6 | Improved Bus Services Mickleton to Moreton-in-Marsh | Current services offer routes to Stratford-Upon-Avon, Chipping Campden and Moreton-In-Marsh. Frequency is approximately every one to two hours with early and late travel options available. No services exist to nearby Evesham. This intervention would look at improving frequency of the current offering whilst also adding connections to Evesham in line with new population. Nearby Warwickshire also has some sites nearby in REG18 so there is potential for collaboration. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic8 | Mickleton to Ebrington Primary School AT Flag | Baker's Hill, Hidcote Road are expected to become unsuitable to cycle. Part of the route sits on the existing national 42 cycle route. Mitigations that could be effective at retaining the cycle routes suitability include: 20mph along the stretch with included enforcement however this is unlikely to be viable across such a long stretch of rural road therefore share pathway segregation utilising bridleway for some of it. | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | Multi-academy trust; GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic9 | Mickleton to Willersey speed route treatment | Reduction of Willersey Speed Limit to 20mph and "route treatment" to Mickleton. Could be potentially extended into Mickleton. | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Important | 75000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 75000 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo1 | Moreton-in-Marsh to Bourton-on-the-Water via Stow-on-the-Wold active travel link | An LTN1/20 compliant route from Moreton-In-Marsh to Bourton-on-the-Water via Stow-in-the-Wold. This route can either be in the form of a segregated addition to the Fosse Road or along the routes identified in the GCC countywide LCWIP (Evenload Road-Chapel Street-Ex railway alignment). The latter was estimated to need ~1-2million to deliver and the latter is assumed | 05_Transport | 05_Active travel / public realm | City Science/GCC LCWIP | Essential | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo10 | Moreton-in-Marsh New Road | South eastern portion of the link road around Moreton-in-Marsh to the East in an attempt to move through traffic and some development traffic away from currently constrained double roundabout. In order to remain inline with the vision to not induce increased car use this should include a wider array of measures including the potential to be car capacity neutral by e.g. pedestrianising or semi-pedestrianising the high street. | 05_Transport | 05_Highways | GCC/CDC/WSP | Critical | 37450252 | Bentley V2 costing report, subject to confirmation on length of road and specification, as set out in the Moreton-in-Marsh feasibility study | 0 | S106; S278; Homes England forward funding | 02: 2027-2037 (inclusive) | GCC Highways; Strategic Site landowners | Delivery approach and cost based on the phased implementation of the access road across applications and aligned to the agreed masterplan, rather than pooled funding and delivery by GCC | Cost to be refined on revised length | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo12 | Moreton-In-Marsh to Chipping Campden Greenway | A quiet street and infrastructure approach to delivering a car-lite route from Moreton-In-Marsh to Chipping Campden. This largely would be upgrades the current 442 national cycle route and could include closure/one-way/speed treatments on one leg of the triangle near Batsford, work on the crossing at station road and lanes or shared pathways along areas of the road that can facilitate it. Alternatively a route could be pursued through upgrading of Rights of Way footpaths along the railway line via Paxford - this route is flatter but may be harder to deliver. Also to note that it opens up railway access for Chipping Campden including sites being delivered there | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo13 | Moreton-In-Marsh to Shipston-on-Stour Cycleway | Greenway from Moreton-in-Marsh to Shipstone-on-the-Stour. This could utilise the verge to make a shared pathway along Todenham Street and joining to an upgraded Bridleway to Shipston-on-Stour. It should be noted that there may be grounds for cross-collaboration over the border with development along this route | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 1500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo16 | Evenlode Improvements | Currently part of the National 48 and the 442 cycle routes and all cyclists are expected to mix with general traffic. The high amount of additional traffic from developments along the route means that cycling is likely to become unsuitable for most people. It is likely that to remain suitable some form of segregation is likely to be required. There is a marginal possibility that limiting speed along the road to 20mph as well with measures to decrease or reroute traffic may retain the route as suitable for some people | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 350000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo17 | Moreton-in-Marsh Station Improvements | Upgrades to the facilities of the station in line with high patronage including better active travel connections. | 05_Transport | 05_Public transport - Rail | City Science modelling | Critical | 3500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | GWR, Network Rail |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo18 | 20mph zones | Introducing 20mph zones across Moreton-in-Marsh (excluding A44 and A429) | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo2 | Blenheim Meadow AT routes upgrade | Upgrading the traffic-free paths through Blenheim Meadow to be suitable for cycling. Current paths cycling is not allowed and there are key barriers along the route. Upgrading these including widening and removal of barriers/gates will allow the developments further away from the centre to use cycling to access the town centre and railway station. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo3 | A44 Corridor Active Transport Route | From edge of Fire Service College Site to High Street roundabout on A44. A combination of measures including a shared pathway or pathway and cycleway up to the junction with Evenload Road where geometric constraint may need a different approach e.g. speed limit reductions or alternative routing. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo4 | Southern Moreton greenway | Footpaths HMM8 and HMM18 to be upgraded to shared green way and options explored to facilitate onwards routing in a low traffic environment, possibly through allotments and through quiet East Street. Facilitating traffic free travel from southern sites to town services. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo5 | BRT Route C09/C08 Moreton-in-Marsh to Cheltenham | BRT Route C09/C08 Moreton-in-Marsh to Cheltenham | 05_Transport | 05_Public transport - Bus | WSP/GCC | Essential | 3500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo8 | Moreton-in-Marsh Transport Hub, parking and road space reallocation | Moving the predominant parking away from the High street to free up capacity on the road for other uses including any road adjustments required and a higher focus on placemaking activities and improved Active Travel facilities. It could include utilisation of parking pricing to further dis-incentivise the use of private vehicles. Includes "Park and Stride" facilities which are simply redistributed parking away from high street with branding and guided walking routes to high street. | 05_Transport | 05_Active travel / public realm | City Science/Moreton-in-Marsh Neighbourhood Plan | Critical | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC; Town and Parish Councils |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo9 | On site provision of services | On-Site provision of key services such as retail and healthcare. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
District-wide | All sites | TRA1 | EV Charging Provision | Providing Additional EV charging infrastructure for public use in addition to provision within new homes, This could also feature incentives e.g. pricing to encourage uptake. | 05_Transport | 05_Behaviour change | City Science modelling | Important | Included in CIL | N/A | 0 | CIL | 07: Phased in line with delivery | GCC Highways |  |  | No | Draft for comment
District-wide | All sites | TRA1 | Travel Plan and Monitor and manage measures | smaller scale interventions to improve safety and implement TROs, improvements to expanded schools , additional bus stop infrastructure - identified where specified but to be derived by TAs | 05_Transport | 05_Behaviour change | Cotswold DC | Essential | Included in CIL | N/A | N/A | S106; S278; CIL | 07: Phased in line with delivery | GCC Highways |  |  | No | Draft for comment
Mickleton | Mickleton Sub area | TRA2 | Enhancements to North Cotswolds Robin Community Bus | Improving the frequency of The Robin within Mickleton. | 05_Transport | 05_Public transport - Bus | City Science modelling | Essential | Included in CIL | N/A | 0 | CIL | 07: Phased in line with delivery | GCC Highways |  |  | No | Draft for comment
Moreton-in-Marsh | North Cotswold Sub area | TRA3 | North Cotswold Line transformation | A series of improvements including doubling of the line leading to the a doubling of the frequency (to 2 trains per hour) and improved speed which would further make routes along this line such as Oxford-Worchester and London (and onto further connections) more time competitive with private modes. SOBC estimated the whole cost of this improvement to be £199 million but includes enabling of more housing in Oxfordshire so delivery could be partly delivered by this too. | 05_Transport | 05_Public transport - Rail | North Cotswold Line Taskforce | Regionally significant | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | 0 | S106; CIL | 07: Phased in line with delivery | GWR, Network Rail | The Local Plan growth is not predicated upon the delivery of the Cotswold Line Transformation but is a project supported by CDC, who will consider using CIL to contribute to early feasibility work. |  | No | Draft for comment
District-wide | North Cotswold Sub area | XXMO1+ | Kingham Station-Stow-on-the-Wold-Bourton-On-The-Water Greenway | Active Travel route | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | Included in CIL | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment. | Included in CIL | CIL | 07: Phased in line with delivery | GCC | This scheme is supported as a wider aspiration but is not identified by the Local Plan evidence base as linked to proposed growth |  | No | Draft for comment

## Summary
Relevant Sub area | Total cost in category | Site/Sub area | Number of schemes | Total cost in category | Total homes | Estimated per unit costs | Infrastructure category | Total cost in category | Prioritisation | Total cost in category
District-wide | 48713843.6923 | All sites | 28 | 58713843.6923 | 15158 | 3873.4558 | 01_Education | 221322260 | Regionally significant | 0
Multiple | 0 | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | 8 | 37850000 | 5248 | 7212.2713 | 02_Community and social infrastructure | 15870968 | Critical | 124070252
Ampney Crucis | 0 | Multiple: SW Cirencester (Kemble and Steadings) | 0 | 0 | 2214 | 0 | 03_Primary Healthcare | 2034256 | Essential | 219531519.27
Cirencester | 107410941.69 | Ampney Crucis Sub Area | 0 | 0 | 0 | #DIV/0! | 04_Open space and Sports | 25717878.9623 | Important | 78538843.6923
Down Ampney | 29735776.18 | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | 0 | 0 | 0 | #DIV/0! | 05_Transport | 157195252 | TBC | 0
Driffield | 36508843.62 | Circencester Sub area | 13 | 2850000 | 4377 | 651.1309 | 06_Utilities | 0
Fairford | 27523815.61 | Cirencester - Strategic - Steadings southern extension (1x landowner) | 14 | 21153579.56 | 1364 | 15508.4894 | 07_Emergency services | 0
Kemble | 20682966.6 | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 7 | 19157305.28 | 1368 | 14003.8781 | 08_Flood Management | 0 | Total check | 422140614.9623
Mickleton | 22911110 | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 11 | 10824421.73 | 613 | 17658.1105
Moreton-in-Marsh | 82163062 | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | 8 | 5175635.12 | 372 | 13912.9976 | Total check | 422140614.9623
North Cotswold | 17620180 | Down Ampney Sub area | 0 | 0 | 1663 | 0
South Cotswold | 28870075.57 | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 14 | 29735776.18 | 1658 | 17934.7263
|  | Driffield Sub area | 0 | 0 | 2225 | 0
|  | Driffield - Strategic - Land south of Driffield (2x landowners) | 13 | 36508843.62 | 2222 | 16430.6227
Total check | 422140614.9623 | Fairford Sub area | 2 | 2000000 | 1439 | 1389.8541
|  | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 17 | 25523815.61 | 1141 | 22369.6894
|  | Kemble Sub area | 4 | 410000 | 1047 | 391.595
|  | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 18 | 20532966.6 | 1019 | 20150.1144
|  | Mickleton Sub area | 2 | 0 | 1505 | 0
|  | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | 11 | 22911110 | 1238 | 18506.5509
|  | Moreton-in-Marsh Sub area | 1 | 0 | 2435 | 0
|  | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 18 | 82163062 | 2217 | 37060.47
|  | North Cotswold Sub area | 10 | 17760180 | 1010 | 17584.3366
|  | South Cotswold Sub area | 5 | 28870075.57 | 1368 | 21103.8564
|  | Multiple: Ampney St Peter STW | 1 | 0
|  | Total attributed | 205
|  | Total Schemes | 205
|  | Schemes requiring attribution | 0

## Validation
Infrastructure category | Infrastructure sub-category | Prioritisation | Initial phasing (27-32;33-37; 38-43) | Relevant Sub area | Attribution | Each item | Site/Sub area | Status of agreement (to be deleted)
01_Education | 01_Early years | Regionally significant | 01: 2027-2032 (inclusive) | District-wide | All sites | All sites | All sites | Draft for comment
02_Community and social infrastructure | 01_Primary | Critical | 02: 2027-2037 (inclusive) | Multiple | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Ampney Crucis Sub Area | Multiple | Agreed in principle
03_Primary Healthcare | 01_Secondary | Essential | 03: 2033-2037 (inclusive) | Ampney Crucis | Multiple: SW Cirencester (Kemble and Steadings) | Circencester Sub area | Circencester Sub area | Fully agreed
04_Open space and Sports | 01_Post 16 | Important | 04: 2038-2043 (inclusive) | Cirencester | Ampney Crucis Sub Area | Down Ampney Sub area | Cirencester - Strategic - Steadings southern extension (1x landowner)
05_Transport | 02_Multifunctional community space | TBC | 05: 2033-2043 (inclusive) | Down Ampney | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | Driffield Sub area | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter)
06_Utilities | 02_Library |  | 06: 2027-2043 (inclusive) | Driffield | Circencester Sub area | Fairford Sub area | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter)
07_Emergency services | 02_Burial ground/cemeteries |  | 07: Phased in line with delivery | Fairford | Cirencester - Strategic - Steadings southern extension (1x landowner) | Kemble Sub area | Cirencester - South East Circencester Strategic sites (South of Preston, Down Ampney and Driffield)
08_Flood Management | 03_GP space |  | TBC | Kemble | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | Mickleton Sub area | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter)
| 04_Onsite Open space standards |  |  | Mickleton | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Moreton-in-Marsh Sub area | Ampney Crucis - Strategic
| 04_Accessible Green Space |  |  | Moreton-in-Marsh | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | North Cotswold Sub area | Cirencester - Non-strategic site allocations in Principal Settlements
| 04_Allotments |  |  | North Cotswold | Down Ampney Sub area | South Cotswold Sub area | Siddington - Non-strategic site allocations in Principal Settlements
| 04_Play area |  |  | South Cotswold | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | Ampney Crucis - Strategic - Ampney Crucs (1x landowner) | Cirencester sub area parishes
| 04_Sport and recreation |  |  |  | Driffield Sub area | Cirencester - Strategic - Steadings southern extension (1x landowner) | Down Ampney Sub area
| 04_SANG provision |  |  |  | Driffield - Strategic - Land south of Driffield (2x landowners) | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters)
| 05_Active travel / public realm |  |  |  | Fairford Sub area | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Down Ampney - Non-strategic site allocations in Non-Principal Settlements
| 05_Behaviour change |  |  |  | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Down Ampney sub area parishes
| 05_Highways |  |  |  | Kemble Sub area | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | Driffield Sub area
| 05_Public transport - Bus |  |  |  | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | Driffield - Strategic - Land south of Driffield (2x landowners) | Driffield - Strategic - Land south of Driffield (2x landowners)
| 05_Public transport - Rail |  |  |  | Mickleton Sub area | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Driffield sub area parishes
| 05_Supporting Sustainable transport integration |  |  |  | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | Fairford Sub area
| 06_Electricity supply |  |  |  | Moreton-in-Marsh Sub area | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Fairford - Strategic - Land north-east of Fairford (1x landowner)
| 06_Water Supply and Wastewater |  |  |  | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Fairford - Non-strategic site allocations in Principal Settlements
| 06_Digital |  |  |  | North Cotswold Sub area | North Cotswold Sub area | Fairford sub area parishes
| 07_Police |  |  |  | South Cotswold Sub area | South Cotswold Sub area | Kemble Sub area
| 07_Ambulance |  |  |  | Multiple: Ampney St Peter STW |  | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter)
| 07_Fire and rescue | [5 empty] | Kemble sub area parishes
| 08_Offsite mitigation | [5 empty] | Mickleton Sub area
| 08_Onsite mitigation | [5 empty] | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters)
Mickleton - Non-strategic site allocations in Principal Settlements
Mickleton sub area parishes
Moreton-in-Marsh Sub area
Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters)
Moreton-in-Marsh - Non-strategic site allocations in Principal Settlements
Moreton-in-Marsh sub area parishes
North Cotswold Sub area
Blockley - Non strategic site allocation in principal settlement
Bourton-on-the-Water - Non-strategic site allocations in Principal Settlements
Chipping Campden - Non-strategic site allocations in Principal Settlements
Stow-on-the-Wold - Non-strategic site allocations in Principal Settlements
Upper Rissington - Non-strategic site allocations in Principal Settlements
Willersey - Non-strategic site allocations in Non-Principal Settlements
North Cotswold sub area parishes
South Cotswold Sub area
Lechlade-on-Thames - Non-strategic site allocations in Principal Settlements
Tetbury - Non-strategic site allocations in Principal Settlements
Coln St Aldwyns, Hatherop, Quenington - Non-strategic site allocations in Non-Principal Settlements
Poulton - Non-strategic site allocations in Non-Principal Settlements
Kempsford - Non-strategic site allocations in Non-Principal Settlements
South Cotswold sub area parishes

## v4 Transport for reference
Option ID | Short title | Source | Description | Indicative High Level Cost | Evaluation of Intervention Importance to Local Plan | Status | Growth Area/Strategic Site
XXMO1+ | Kingham Station-Stow-on-the-Wold-Bourton-On-The-Water Greenway | AK CDC | Active Travel route | 2000000 | Important | Proposed | All
Ac1 | On-site services | City Science | This site represents a singificant expansion of an existing village to the north. At present there is extremely limited services around the village including a small village hall, a small primary school (~100 pupils), a small play park and green space and a small church. The level development (660 dwellings) combined with the more isolated nature of the site (~5miles from Cirencester which is likely to be where most services are for the housing). It is approximately 2-2.5 miles from the Driffield Site. The scale of the development suggests that it would require at least an additional primary school, a retail offering ideally with a sizable convience shop and/or postal facilities collection/delivery and a third space such as community centre | 0 | Critical | LP: On-site | Cotswold: Ampney Cruicis
Ac2 | Enhancements to 50 Bus | City Science | Currently the 50 bus provides a circularly route between Cirencester and Amney Cruicis Monday to Friday between 8:50 13:50. This intervention will increase the frequency of the bus from hourly to half-hourly and extend the times to 0730 to 1830 (to allow for work time commuting). In addition services would run a more limited service on saturday and sunday (at present there is no services. Given the level of current provision an additional vehicle would likely be needed. | 500000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Ac3 | Active Travel route to join D7 (access to Down Ampney, Driffield Site and Cirencester) | City Science | An active travel route including cycling and walking to join onto intervention D7 to provide a route between all the major sites and Cirencester. This route is 2.1km long and would be formed through small bit of shared pathway on the A417 between Village Street and Waterton Farm (BAC25 footpath) 0.4km followed by 1.7km of upgraded footpath to shared space. | 1000000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Ac4 | Ampney Cruicis-Poulton-Fairford Active Travel Route | City Science | An active travel route providing a route to Poulton including Ampney St Peter. 3.4km predominantly upgraded bridleways, footpaths and tracks followed by 1.3km of quiet lane treatment, 1.6km of on road segregation followed by 3.2km of quiet lane treatment on Welsh Way. The whole route is 8.6km. | 4000000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Ac5 | Amney Cruicis 20mph zone | City Science | 20mph within Ampney Cruicis including new residential streets, village street, school lane, butchers arm lane, alloment lane, and riding lane (from the northern edge of the site to ashbrook lane junction) | 100000 | Critical | LP: Local access | Cotswold: Ampney Cruicis
Ac6 | Diversion of 77 through Village Street | City Science | Diversion of the 76/77 bus route through Ampney Crucis. This will provide bus services to fairford and additional services to circencester | 100000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Ac7 | Segregated Active Travel Route on Access Road and B4425 | City Science | Route along new access road and then extend and enhance segregated cycleway within road boundary, | 2500000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Cir2 | Spratsgate Lane/Somerfield Road active travel links | City Science | Package of active travel measure could include providing pedestrian footpaths for residents willing to walk into Cirencester, as well as a on-road segregated cycleway. Require active travel access points along Spratsgate Lane for Sites SD20 and C190 | 1400000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir3 | Active travel access Swindon Road | City Science | Active travel access onto Swindon Road at the northeastern corner of Site R519 to give access to existing cycleway crossing the A419 and along Cricklade Road to town centre. | 200000 | Critical | LP: Local access | Cotswold: Cirencester
Cir4 | Cricklade Road Cycleway Enhancement | City Science | Upgrade the cycleway from Preston Toll Bar along Cricklade Road by installing high-quality road surface throughout, introducing a designated on-road cycle lane, and implementing clear signage. Extend this cycleway improvements to the town centre, passing under the foot tunnel under the Bristol Road and joining Watermoor Way | 2000000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir5 | Watermoor Road road space reallocation | City Science | Reallocate road space along Watermoor Road to create a serrated cycleway, joining with Cycleway improvements in Cir4 to provide active travel links for southern development sites into Cirencester. | 250000 | Critical | LP: Local access | Cotswold: Cirencester
Cir6 | Internal active travel links for Site R650 | City Science | Internal active links connecting Site R650 to Site R519 to benefit from active travel access towards town centre suggested in Cir4 and Cir5. | 0 | Critical | LP: Local access | Cotswold: Cirencester
Cir7 | Active travel access on Kingshill Lane | City Science | Active travel access on western boundary of site directly opposite off road leading to Cirencester skate park. | 150000 | Critical | LP: Local access | Cotswold: Cirencester
Cir8 | Queen Elizabeth Road/Beeches Road cycleway | City Science | On road cycleway connecting to existing east-west cycle route to link Sites R650 and R519 to town centre. Include on road cycleways along Queen Elizabeth Road and Beeches Road. Then a segregated cycle lane along London Road/Lewis Lane to access town centre. | 1000000 | Critical | LP: Local access | Cotswold: Cirencester
Cir9 | Pedestrianise Castle Street | City Science | Extend current pedestrian zone restrictions to on Crickade Road to cover Castle Street for more attractive placemaking in town centre. Reallocate road space to active travel infrastructure and green space. Divert East West traffic along Park Lane, Black Jack Street, Market Place and The Waterloo to reach London Road | 100000 | Important | LP: Strategic (off-site) | Cotswold: Cirencester
Cir10 | Siddington Road Cycleway | City Science | Provision of an on-road cycleway connecting Sites SD23 and SD17 to town centre via Siddington Road. Cycleway would follow Siddington Road then turn onto Kingsmead Road to connect to existing cycleway underpass under Bristol Road. To be delivered along with Cir5 to provide onwards cycle access to town centre. | 300000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir11 | Extend London Road cycleway | City Science | Extend London Road cycleway next to Site C81B toward town centre with on-road cycle lane. Connect to existing active travel bridge over Swindon Road, creating a shared use path for pedestrians and cyclists. Rejoin cycleway to London Road and towards town centre with | 500000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir12 | Enhancement to 882 bus service | City Science | Increase the frequency of the Stagecoach West 882 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 400000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir14 | Cirencester mobility hub | Cotswold DC | Development of a new or enhanced mobility hub integrating public transport, micromobility, cycle facilities, and shared mobility options | 1000000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir15 | Cirencester Park and Ride | Cotswold DC | Park and ride/stride provision to intercept car trips at the edge of town, with potential for targeted bus priority measures to improve reliability and attractiveness of services into Cirencester. Park and Rides tend to target cars coming from out of town. Given the placement of this it is unlikely to be used by sites within the local plan. It is will be important for reducing overal traffic levels which may help local plan traffic however at present the modelling does not suggest it is critical for the functioning of the network | 10000000 | Important | LP: Strategic (off-site) | Cotswold: Cirencester
Cir16 | Wayfinding improvements | Cotswold DC | Introduction of a coherent, high-quality wayfinding strategy to improve navigation, reinforce key destinations, and enhance the legibility of walking and cycling networks across the town. | 500000 | Important | LP: Strategic (off-site) | Cotswold: Cirencester
Cir17 | East-West Pedestrian / Cycle route improvements | Cotswold DC | Strengthening east–west pedestrian and cycle connectivity across Cirencester, improving continuity, safety, and accessibility. | 500000 | Important | LP: Strategic (off-site) | Cotswold: Cirencester
Cir18 | Tesco–Siddington Road Active Travel Link | Cotswold DC | Creation of a direct, safe walking and cycling route connecting Tesco to Siddington Road, improving local accessibility and reducing short car trips. | 250000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir19 | Orchard Fields–Steadings Active Link | Cotswold DC | Establishment of a walking and cycling route through Orchard Fields connecting Siddington to The Steadings. | 375000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir20 | Siddington–South Cerney active travel link | Cotswold DC | Development of a strategic active travel corridor utilising the disused railway line to provide a direct, segregated walking and cycling link between Siddington and South Cerney. | 1100000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir21 | Green Lane Quiet Road | Cotswold DC | Reclassification of Green Lane (off Clark’s Lane) from highway use to a quiet lane with lower speed limits and appropriate signage to enable shared use road for walking and cycling. | 100000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir22 | Dower's Lane and A417 Underpass Roundabouts Active Travel Mitigation | City Science | Model suggests that cycling along the Dower's Lane becomes unsuitable for most people from suitable for some people due to increased traffic volumes. Many surrounding roads are currently assessed to have low suitability for cycling however there are a few off-road routes nearby meaning some cycle routing may be happening. Mitigation is likely to involve speed limit treatment on Dower's Lane and a shared pathway/cyclops upgrade to the two roundabouts. There is limited suitability in the wider area for cycling so this is unlikely to be a critical mitigation | 250000 | Not Important | Proposed | Cotswold: Cirencester
Cir23 | Spratsgate Lane AT Mitigation | City Science | At present the road has minimal segregated infrastructure (with the exception of the new roundabout that feeds into the development near the Wilkinson Road Junction). The change is traffic is significant enough that even with minimal interventions such as 20mph zones and traffic calming or non-segregated cycle lanes are unlikely to be sufficient to leave the road suitable for most people. At present this route lies on the National Route 45. Multiple options should be explored including providing segregated provision or through alternative routing for the key routes that may use this route. For example K10 intervention may open up a route through Chesterton Farm and into the town centre and to east provision could be improved for a route along love lane. These interventions would be in addition to that proposed as part of the commited steadings site. | 1400000 | Critical | Proposed | Cotswold: Cirencester
Cir24 | On site provision of services | City Science | Site further from Cirencester Town centre require on site provision of essential services to reduce travel in to the town centre. This should include at a minimum a primary school, a community space, a retail offering (ideally a small convience store and service for last mile delivery such a RM parcel box and parcel collection (either within a retail offering or through an external parcel collection service). | 0 | Critical | LP: On-site | Cotswold: Cirencester
Cir25 | Kingshill Road/London Road mitigation | City Science | Upgrade Junction to a signalised Junction​ | 250000 | Critical | Proposed | Cotswold: Cirencester
Cir26 | Kingshill Road/Cirencester Road mitigation | City Science | Upgrade Junction to a signalised Junction​ | 250000 | Critical | Proposed | Cotswold: Cirencester
Cir27 | Somerford Road/Chesterton Lane HW Mitigation | City Science | Upgrade intersection between somerford road and chesterton lane to be signalised. The modelling suggests that increased traffic on Chesterton road will lead to severe queueing on the Somerford road due to them being unable to merge | 250000 | Essential | Proposed | Cotswold: Cirencester
Cir28 | Cirencester Road AT Flag | Ciry Science | Limit issues for active travel using speed limits (20mph) and soft segregation | 400000 | Critical | 0 | Cotswold: Cirencester
Cir29​ | B4425/A429 Stow Road mitigation ​ | City Science | Signal Optimisation/ Increase cycle time (reduce amount of loss time for Cherytree Ln and increase green time B4425 and Stow Rd)​ Required to deal with harm to network​ | £10-50k​ | Critical | Proposed | Cotswold: Cirencester
Cir30 | Cirencester-Swindon BRT | City Science | Implementation of BRT route prosed between Cirencester and Swindon. This is assumed to contain enough bus priority interventions to keep the journey times down and a service that is frequent a minimum of every fifteen minutes. In order to maximise the utility of thise route for the local plan it is assumed that this will be an express stopping service that would call at Swindon-Down Ampney-Driffield Junction- Preston-Kingshill Lane-Cirencester. This captures around 2300 dwellings in the local plan. Journey time between Swindon and Cirencester should be no longer than 50-60 minutes to provide a competitive journey time to driving. | 5000000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir31 | Active travel connections with and through The Steadings | City Science | Connection of Cirencester to Kemble active travel route to the south side of The Steading site, with active connections through the site to allow onwards active travel to Cirencester. | 0 | Critical | LP: Local access | Cotswold: Cirencester
Cir32 | Enhanced or extended bus service between Site C187 via the Steadings to Cirencester | City Science | Increase the frequency of existing bus routes or implementation of a new bus route to connect the new site south of the Steadings via The Steadings to Cirencester. Could include a bus gate to permit bus movements between the Steadings and site C187. | 150000 | Critical | BAU+ | Cotswold: Cirencester
Cir33 | Local transport corridor interchange hub in The Steadings | City Science | Implement a Local Transport Corridor Interchange Hub within The Steadings where bus service between The Steading and Cirencester will stop on site. | 0 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir34 | 20mph zones | City Science | Extended the 20mph zones to cover residential street and development sites. This follows the consultation currently out | 150000 | Essential | LP: On-site | Cotswold: Cirencester
Cir35 | Active Travel Route from South Steadings to Tetbury Road Entrance of Agricultural College | City Science/ GCC | Route following the existing planned interconnection between the Steadings and South Steadings extension. Exiting on the southern access from the Steadings (assuming the roundabout has been designed with adequate segregation. Then 0.2km of shared pathway on the north bound side of the road. Given the likely low volumes of both pedestrians and cyclists a 3m shared pathway would be sufficient and can be delivered within the HW boundary | 100000 | Critical | LP: Local access | Cotswold: Cirencester
Cir36​ | A419 Swindon Road/Silver Street | City Science | Upgrade the junction to a signalised junction and add approach flares. | ~0.5-1million | Critical | Proposed | Cotswold: Cirencester
Cir37 | A429/Chesterton Ln Junction​ | City Science | Change the stages and phases (having an all A429 stage followed by a Chesterton ln stage, and more green time for Stroud lane approach) ​ | £10-50k​ | Critical | Proposed | Cotswold: Cirencester
Cir38 | A419 Stroud Road/Trewsbury Road | City Science | Upgrade the junction to a signalised junction and add approach flares. | ~0.5-1million | Critical | Proposed | East of Cirencester
Cir39 | A429 Watermoor Roundabout | City Science | Add approach arm flares to the roundabout and widen the eastbound approach arm. | £1-10million​ | Critical | Proposed | Cotswold: Cirencester
Cir40 | Stroud Road north of Tetbury Roundabout | City Science | Widen the road to two lanes to accommodate development access. | £1-10million​ | Critical | Proposed | Cotswold: Cirencester
Cir41 | A419 Swindon Road\Cirencester Road | City Science | Widen the roundabout to provide two lanes between the roundabout and the Kingsmill Lane signalised junction. | £1-10million​ | Critical | Proposed | Cotswold: Cirencester
Cir42 | A29 Swindon Road/Bristol Road Roundabout | City Science | Widen the roundabout. | £1-10million​ | Critical | Proposed | Cotswold: Cirencester
D1 | On site provision of services | City Science | Site requires on-Site provision of key services such as retail and healthcare as there is currently only one small village shop in Down Ampney, with other retail and healthcare services located over 3km away. | 0 | Critical | LP: On-site | Cotswold: Down Ampney
D2 | Cricklade cycle route | City Science | Cycleway connecting Down Ampney and Cricklade to give sustainable access to retail services in Crickade. Route would follow Down Ampney Road and head south on Cirencester road, cross the A419 and continue down into Crickade. | 900000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D3 | South Cerney cycle route | City Science | Cycleway connecting Down Ampney and Cricklade to give sustainable access to retail services in South Cerney. Route would follow Down Ampney Road west and cross the A419, before turning north onto Cerney Wick Lane and following north on to Station Road into the centre of South Cerney. | 1750000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D4 | Driffield Junction Development cycle route | City Science | Cycleway connecting Down Ampney to Driffield Junction Development via existing bridleway to the north of the development Site. Route meets the eastern boundary of the Driffield Junction Development Site, where, in conjunction with Option DJ3 it would benefit from onwards cycle access to Cirencester. | 1500000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D6 | Enhancements of 76 bus route | City Science | Increase the frequency of the Stagecoach West 76 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 1000000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D7 | Down Ampney -Cirencester Greenway | Cotswold DC | Extended greenway linking Sites in Down Ampney to Cirencester. Route would extend up through the sites in Down Ampney, north along the PROW route (BDA1) and the west towards Driffield (Route BDD16). It would then connect with the sites at Driffield Junction Development, running directly through these sites and onwards to the existing bridleway running northeast from Harnhill and adjacent to the A419. It would cross the A417 at Witpit Lane and connect to the sites along Kingshill Lane. For there it would follow Cir8 into town centre. | 3500000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D9 | 20 mph zones | City Science | Introducing 20mph zones across Down Ampney including within development sites | 75000 | Essential | LP: Strategic (off-site) | Cotswold: Down Ampney
DJ1 | On site provision of services | City Science | Site requires on-Site provision of key services such as retail, education and healthcare as closest services are 2 miles away in South Cerney or Down Ampney. | 0 | Critical | LP: On-site | Cotswold: Driffield Junction Development
DJ2 | South Cerney active travel route | City Science | Provision of a segregated cycleway linking the western boundary of the Site to services in South Cerney for those who are able to cycle the distance. This could include active travel priority at A419/B4696 junction, then an onwards active travel route along the B4696 and Station Road into South Cerney. Alternatively could explore an active travel bridge over A419 connecting to and active trave route along Bow Wow Road directly into South Cerney. This assumed D3 is delivered | 200000 | Critical | LP: Strategic (off-site) | Cotswold: Driffield Junction Development
DJ3 | Cirencester active travel route | City Science | Provision of a segregated cycleway connecting the Site to Cirencester via Cirencester Road for those able to cycle the distance. It is assumed that this should be delivered using a crossing of Cirencester Road which requires a change in the character of that road. GCC expressed support for this. | 3000000 | Critical | LP: Strategic (off-site) | Cotswold: Driffield Junction Development
DJ5 | Driffield Junction Development Village Mobility Hub | City Science | A smaller mobility hub providing bus services, EV charging and parcel drop off points. | 1500000 | Critical | LP: Strategic (off-site) | Cotswold: Driffield Junction Development
DJ6 | Charlham Lane access | City Science | Active travel access to Charlham Lane to facilitate onward active travel to Primary school and shop. Much of this is covered by D4 but this just ensures the access is secured in the masterplan | 0 | Critical | LP: Local access | Cotswold: Driffield Junction Development
DJ8 | Bridleway enhancement to Down Ampney (Wiltshire) | City Science | Enhancement of Bridleways through Wiltshire to high quality cycleway and walking route to Down Ampney | 750000 | Critical | LP: Strategic (off-site) | Cotswold: Driffield Junction Development
DJ9 | Future Proofing for Post-Local Plan Growth | City Science | Ensuring that internal design accounts for future post-local growth particularly around the prevention of through-traffic | 0 | Critical | LP: On-site | Cotswold: Driffield Junction Development
DJ10​ | B4696 Spine Rd Approach to Station Rd/Cerney Wick Ln Intersection​ | City Science | Upgrade Junction to a signalised Junction​ | 250000 | Critical | Proposed | Cotswold: Driffield Junction Development
Fa1 | On-site provision of services | City Science | On-Site provision of key services such as retail and healthcare. | 0 | Critical | LP: On-site | Cotswold: Fairford
Fa2 | Southrop Road/London Road active travel route | City Science | Provision of a segregated active route linking Site F57C to the town centre via Southrop Road and London Road. Package of measures include ensuring filling in gaps in pedestrian infrastructure and ensuring continuous footpaths and adequate crossing facilities, as well as enabling a shared used road with a cycleway. Requires active travel access of the southern boundary of the large Site along Hatherop Road and active travel access of the northern boundary of the large Site south of Southrop road. | 0 | Critical | LP: Local access | Cotswold: Fairford
Fa3 | Hatherop Road active travel route | City Science | Provision of an active route connecting Site F57B to the town centre via Hatherop Road. Measures could include widening existing footpaths in some areas and, ensuing adequate crossing facilities and implementing shared used road with a cycleway. Requires active travel access to Site along northwestern boundary along Hatherop Road. | 2000000 | Critical | LP: Local access | Cotswold: Fairford
Fa4 | Trubshaw Way active travel access | City Science | Active travel access to Trubshaw Way for Site F20A for onward active travel to town centre. | 0 | Critical | LP: On-site | Cotswold: Fairford
Fa5 | Cinder Lane quiet road | City Science | Designation of Cinder Lane as a quiet road, to encourage active travel from Site F20A to the Town centre. Requires active travel access to Cinder Lane on northern boundary of Site. Includes surfacing upgrade. | 380000 | Critical | LP: Local access | Cotswold: Fairford
Fa6 | Horcott Road active travel route | City Science | Improve active travel links along Horcott Road to encourage sustainable access from Site F53A to the town centre. This includes by widen footpaths and improving crossing over wide-mouth junctions heading to town centre, as well as introducing a cycleway. This could connect to existing the cycleway crossing Dilly's Bridge and connecting to Gas Lane, providing a more direct route to High Street. | 620000 | Critical | LP: Local access | Cotswold: Fairford
Fa7 | E End active travel access | City Science | Provision of an active travel access from the western boundary of the Site F20A, enhancing the existing footpath the connects to E End | 0 | Critical | LP: Local access | Cotswold: Fairford
Fa8 | Leafield Road Crossing | City Science | Provision of pedestrian crossing connecting Site to the east of Leafield Road to the Primary School opposite. | 140000 | Critical | LP: Local access | Cotswold: Fairford
Fa9 | Leafield Road active travel route | City Science | Providing footpaths along Leafield road and a cycleway to enable active travel into town centre from Site F57A. | 0 | Critical | LP: Local access | Cotswold: Fairford
Fa10 | Enhancement to 76 bus service | City Science | Increase the frequency of the Stagecoach West 76 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 350000 | Critical | LP: Strategic (off-site) | Cotswold: Fairford
Fa12 | 20mph zones | City Science | Introducing 20mph zones across Down Ampney including within development sites | 150000 | Critical | LP: On-site | Cotswold: Fairford
Fa13 | Fairford-Lechlade AT Route | City Science | Segregated Cycleway on Park Street (0.3km) followed by quiet lane treatment (with physical calming measures) on Leafield Road (0.5km) followed by footway upgrade to shared space (0.4km), segregated route along Hatherop Lane (0.3km) and then again (shared) along to Slothop Road (2.2km) followed by enhanced of a bridleway (1.6km) finally quiet lane treatment on Hambidge Lane (2.7km). Cost is additional to Fa3 | 800000 | Essential | LP: Strategic (off-site) | Cotswold: Fairford
K1 | A429 Active travel route | City Science | The A429 is the single route currently connecting the K15 sites to Kemble centre. Provide a segregated cycleway along road to improve active travel access to key services and schools in Kemble centre, along with improved continuous footpaths. | 0 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K2 | Access to Old Vicarage Lane | City Science | Active travel access to the south of Old Vicarage Lane of the eastern boundary of Site K12 to allow onwards active travel access to centre of Kemble. | 0 | Critical | LP: Local access | Cotswold: Kemble
K3 | Church Road active travel | City Science | Improvements to active travel along Church Road for Site K12. This includes active travel access to site boundary on Church road, continuous footways and possible exploration of a quiet lane on Church Road with lower speed limits and signage to improve mixed use of road for cycling. | 250000 | Critical | LP: Local access | Cotswold: Kemble
K5 | Improved A429 crossing facilities | City Science | Improved active travel crossing facilities to allow active travel access from Site K12 to access Station Road, for onwards access to Kemble Station. | 100000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K6 | Station Road active travel | City Science | Improved pedestrian footways and cycleways along Station Road to promote active travel access from Sites K12 to Kemble Station | 120000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K8 | Kemble station improvements | GCC (LTP) | Package of improvements including improving accessibility at the station with step free bridge, cycle parking etc. | 2500000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
LP7​ | Stow-on-the-Wold Sheep Street/A429/High Street Mitigation​ | City Science | Change signal stages with indicative arrows at high street/Roman Rd Junctions.​ Signal optimisation at A429/B4068. | ~£90-130k​ | Critical | Proposed
LP8 | Avening High Street AT Mitigation | City Science | Model suggests that Avening High Street becomes unsuitable to most people to cycle on after the local plan. Mixed traffic suitability could be restored if the speed limit is reduced to 20mph with a corresponding amount of traffic calming to ensure the design speed matches the new speed limit. The remainder of links surrounding this one are deemed unsuitable according to LTN1/20 before and after the local plan which means this stretch is unlikely to currently form part of a whole route however there are some non-road routes near by which this may cut off. | 150000 | Critical | Proposed | Cotswold: Kemble
LP9 | Coates AT Mitigation | City Science | Model suggests that cycling on the Trewsbury Road becomes unsuitable for most people due to increased traffic volumes. Caveat: At present all the surrounding rounds into Coates are current deemed to be unsuitable for most cyclists and this is unlikely to block a route. Solutions include implementing a one way system around coates to allow for cycle lanes and/or speed reductions. | 150000 | Essential | Proposed | Cotswold: Kemble
LP10 | B4040/B4696 | City Science | Signal Optimisation | £10-50k​ | Essential | Proposed | In Wiltshire
K10 | Kemble -Cirencester cycleway | GCC (LTP) | Reuse of former rail route as a cycleway connecting Kemble and Cirencester for access to employment and education. | 2000000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K12 | Kemble to Tetbury Service bus service | City Science | New bus service connecting town centre of Kemble, developments Sites and Tetbury, along A439, Oxleaze Road and A433. Modelling suggests 100-200 passengers a day | 400000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K13 | On site provision of services | City Science | Sites require on-site provision of key services such as retail and healthcare as there are minimal key services available in Kemble. | 0 | Critical | LP: On-site | Cotswold: Kemble
K14 | Windmill Road AT Mitigation | City Science | Flag identifies cycling may become unsuitable for most people as a result of increased traffic flow. At present the road is functionally not a full two-way street due to parking on the street. Mitigation could involve removing on street parking given most houses have drives to accommodate segregation | 160000 | Critical | Proposed | Cotswold: Kemble
K15 | Kemble to Ewen Cycle Mitigation | City Science | Model suggests that local plan traffic will make Windmill Road, School Road to Ewen no longer 'suitable for most people'. Mitigation involves shared pathway and reduction to 40mph | 1100000 | Essential | Proposed | Cotswold: Kemble
K20 | 20mph zones | City Science | Introducing 20mph zones across all streets in Kemble, including within the development sites. | 150000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
Mic2 | Site Active Travel Connections and wider offsite improvements to car-free routes | City Science | Active Travel only connections to the public park to provide attractive active travel routes within Mickleton. At present the paths within the park are not sufficient for cycling and so upgrade of widths for a shared pathway or separate cycling routes would be required | 50000 | Critical | LP: Local access | Cotswold: Mickleton
Mic3 | Long Marsdon Road Active Travel Connection | City Science | Cycleway and/or Shared Pathways along Long Marsdon Road to facilitate segregated access to National Cycleway 5 route featuring a fully car-free travel route to Stratford-Upon-Avon the distance being approximated 12-14km/ 7.5-8.5 mi within the distance that some may commute especially if coupled with targeted e-micromobility interventions. | 3500000 | Important | LP: Strategic (off-site) | Cotswold: Mickleton
Mic5 | Mickleton Local Centre and Services Hub | City Science | At present that are limited services within Mickleton itself. Providing a local hub including some GP services, Schools and Retail offerings and mobility hub | 0 | Critical | LP: On-site | Cotswold: Mickleton
Mic6 | Improved Bus Services Mickleton to Moreton-in-Marsh | City Science | Current services offer routes to Stratford-Upon-Avon, Chipping Campden and Moreton-In-Marsh. Frequency is approximately every one to two hours with early and late travel options available. No services exist to nearby Evesham. This intervention would look at improving frequency of the current offering whilst also adding connections to Evesham in line with new population. Nearby Warwickshire also has some sites nearby in REG18 so there is potential for collaboration. | 400000 | Critical | LP: Strategic (off-site) | Cotswold: Mickleton
Mic8 | Mickleton to Ebrington Primary School AT Flag | City Science | Baker's Hill, Hidcote Road are expected to become unsuitable to cycle. Part of the route sits on the existing national 42 cycle route. Mitigations that could be effective at retaining the cycle routes suitability include: 20mph along the stretch with included enforcement however this is unlikely to be viable across such a long stretch of rural road therefore share pathway segregation utilising bridleway for some of it. | 2000000 | Essential | Proposed | Cotswold: Mickleton
Mic9 | Mickleton to Willersey speed route treatment | GCC (20mph Speed Work) | Reduction of Willersey Speed Limit to 20mph and "route treatment" to Mickleton. Could be potentially extended into Mickleton. | 0 | Important | LP: Strategic (off-site) | Cotswold: Mickleton
Mic11 | 20mph zones | City Science | Introducing 20mph zones across all streets in Mickleton, including within the development sites. | 150000 | Critical | LP: Strategic (off-site) | Cotswold: Mickleton
Mo1 | Moreton-in-Marsh to Bourton-on-the-Water via Stow-on-the-Wold active travel link | City Science/GCC LCWIP | An LTN1/20 compliant route from Moreton-In-Marsh to Bourton-on-the-Water via Stow-in-the-Wold. This route can either be in the form of a segregated addition to the Fosse Road or along the routes identified in the GCC countywide LCWIP (Evenload Road-Chapel Street-Ex railway alignment). The latter was estimated to need ~1-2million to deliver and the latter is assumed | 2000000 | Essential | Proposed | Cotswold: Moreton-In-Marsh
Mo2 | Blenheim Meadow AT routes upgrade | City Science | Upgrading the traffic-free paths through Blenheim Meadow to be suitable for cycling. Current paths cycling is not allowed and there are key barriers along the route. Upgrading these including widening and removal of barriers/gates will allow the developments further away from the centre to use cycling to access the town centre and railway station. | 250000 | Critical | LP: Local access | Cotswold: Moreton-In-Marsh
Mo3 | A44 Corridor Active Transport Route | City Science | From edge of Fire Service College Site to High Street roundabout on A44. A combination of measures including a shared pathway or pathway and cycleway up to the junction with Evenload Road where geometric constraint may need a different approach e.g. speed limit reductions or alternative routing. | 1500000 | Critical | LP: Local access | Cotswold: Moreton-In-Marsh
Mo4 | Southern Moreton greenway | City Science | Footpaths HMM8 and HMM18 to be upgraded to shared green way and options explored to facilitate onwards routing in a low traffic environment, possibly through allotments and through quiet East Street. Facilitating traffic free travel from southern sites to town services. | 1000000 | Critical | LP: Local access | Cotswold: Moreton-In-Marsh
Mo5 | Moreton-in-Marsh to Cheltenham BRT | WSP/GCC | BRT Route C09/C08 Moreton-in-Marsh to Cheltenham | 3500000 | Essential | BAU+ | Cotswold: Moreton-In-Marsh
Mo8 | Moreton-in-Marsh Transport Hub, parking and road space reallocation | City Science/Moreton-in-Marsh Neighbourhood Plan | Moving the predominant parking away from the High street to free up capacity on the road for other uses including any road adjustments required and a higher focus on placemaking activities and improved Active Travel facilities. It could include utilisation of parking pricing to further dis-incentivise the use of private vehicles. Includes "Park and Stride" facilities. | 1000000 | Critical | BAU+ | Cotswold: Moreton-In-Marsh
Mo9 | On-site services | City Science | On-Site provision of key services such as retail and healthcare. | 0 | Critical | LP: On-site | Cotswold: Moreton-In-Marsh
Mo10 | Moreton-in-Marsh New Road | GCC/CDC/WSP | South easten portion of the link road around Moreton-in-Marsh to the East in an attempt to move through traffic and some development traffic away from currently constrained double roundabout. In order to remain inline with the vision to not induce increased car use this should include a wider array of measures including the potential to be car capacity neutral by e.g. pedestrianising or semi-pedestrianising the high street. | 37450252 | Critical | Proposed | Cotswold: Moreton-In-Marsh
Mo12 | Moreton-In-Marsh to Chipping Campden Greenway | City Science | A quiet street and infrastructure approach to delivering a car-lite route from Moreton-In-Marsh to Chipping Campden. This largely would be upgrades the current 442 national cycle route and could include closure/one-way/speed treatments on one leg of the triangle near Batsford, work on the crossing at station road and lanes or shared pathways along areas of the road that can facilitate it. Alternatively a route could be pursued through upgrading of Rights of Way footpaths along the railway line via Paxford - this route is flatter but may be harder to deliver. Also to note that it opens up railway access for Chipping Campden including sites being delivered there | 1000000 | Essential | LP: Strategic (off-site) | Cotswold: Moreton-In-Marsh
Mo13 | Moreton-In-Marsh to Shipston-on-Stour Cycleway | City Science | Greenway from Moreton-in-Marsh to Shipstone-on-the-Stour. This could utilise the verge to make a shared pathway along Todenham Street and joining to an upgraded Bridleway to Shipston-on-Stour. It should be noted that there may be grounds for cross-collaboration over the border with development along this route | 1500000 | Essential | LP: Strategic (off-site) | Cotswold: Moreton-In-Marsh
Mo16 | Evenlode Improvements | City Science | Currently part of the National 48 and the 442 cycle routes and all cyclists are expected to mix with general traffic. The high amount of additional traffic from developments along the route means that cycling is likely to become unsuitable for most people. It is likely that to remain suitable some form of segregation is likely to be required. There is a marginal possibility that limiting speed along the road to 20mph as well with measures to decrease or reroute traffic may retain the route as suitable for some people | 350000 | Critical | LP: Local access | Cotswold: Moreton-In-Marsh
Mo17 | Moreton-in-Marsh Station Improvements | City Science | Upgrades to the facilities of the station in line with high patronage including better active travel connections. | 3500000 | Critical | LP: Strategic (off-site) | Cotswold: Moreton-In-Marsh
Mo18 | 20 mph zones | City Science | Introducing 20mph zones across Moreton-in-Marsh (excluding A44 and A429) | 150000 | Critical | LP: Strategic (off-site) | Cotswold: Moreton-In-Marsh
Note on F74: Assumed delivered as part Fa13
Note on F78: Assumed delivery as part of Masterplan

## 260708Transport
Sub area |  | Scheme information |  |  | Categorisation |  |  |  | Cost and delivery
Relevant Sub area | Site/Sub area attribution | Ref | Scheme name | Scheme description | Infrastructure category | Infrastructure sub-category | Source | Prioritisation | Cost (£) | Source of cost | Confirmed funding | Potential funding mechanism | Initial phasing | Potential Delivery partners/ providers | Commentary (to be added to final IDP) | Working Commentary (to be deleted) | Sensitive to growth figure | Status of agreement (to be deleted)
Ampney Crucis | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | 1.111 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 1.112 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 1.113 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 1.114 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 1.115 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 1.116 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 1.117 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 1.118 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | 1.219 | Land north of Mickleton Primary school | 2FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 10357200 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | 1.119 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 1.21 | Land north, east and south of Moreton-in-Marsh | 3 FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 15535800 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 1.22 | Onsite early year provision | Onsite early year provision in primary school | 01_Education | 01_Early years | IDP modelling | Important | Covered under primary school delivery/ privately funded | GCC early years | N/A | S106; commercial funding | 02: 2027-2037 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
District-wide | All sites | 1.122 | Assess Local capacity at application stage | Support within nearby local centre | 01_Education | 01_Early years | IDP modelling | Important | Planning obligation | GCC early years | N/A | S106; commercial funding | 06: 2027-2043 (inclusive) | GCC; Private sector provider | Additional privately run facilities within site local centre will also be supported |  | No | Agreed in principle
Ampney Crucis | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | 1.211 | Ampney Crucis New primary school | 1FE Primary school (room for expansion) | 01_Education | 01_Primary | IDP modelling | Essential | 5178600 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 1.212 | Steading Southern Extension Primary school | 1FE Primary school (room for expansion) | 01_Education | 01_Primary | IDP modelling | Essential | 5178600 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 1.213 | Land south east of Cirencester and south of Preston Primary school | 2FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 10357200 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 1.214 | Land east of Kingshill Lane Primary School | 1FE Primary school (room for expansion) | 01_Education | 01_Primary | IDP modelling | Essential | 5178600 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 1.215 | Land surrounding Down Ampney Primary school | 3FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 15535800 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 1.216 | Land south of Driffield Primary school | 2FE Primary school (room for expansion to 3fe to serve broad location for growth) | 01_Education | 01_Primary | IDP modelling | Essential | 10357200 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 1.217 | Land north-east of Fairford Primary school | 2FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 10357200 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 1.218 | Land south-west of Kemble Primary school | 2FE Primary school | 01_Education | 01_Primary | IDP modelling | Essential | 10357200 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
North Cotswold | North Cotswold Sub area | 1.221 | Financial contributions towards primary delivery | Financial contributions to support delivery of local school expansion (where not provided by strategic sites) | 01_Education | 01_Primary | IDP modelling | Essential | 10751760 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
South Cotswold | South Cotswold Sub area | 1.222 | Financial contributions towards primary delivery | Financial contributions to support delivery of local school expansion (where not provided by strategic sites) | 01_Education | 01_Primary | IDP modelling | Essential | 17311320 | GCC Education (Benchmark per primary pupil of £24,660) | 0 | S106; DfE grant | 02: 2027-2037 (inclusive) | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | All sites | 1.311 | South Cotswold new Secondary | 6FE Secondary school (room for expansion) to be delivered on Land South East of Cirencester and south of Preston | 01_Education | 01_Secondary | IDP modelling | Essential | See see site totals to avoid double counting | GCC Education (Benchmark per Secondary pupil of £29,875 for 900) for £26,887,500 | 0 | S106; DfE grant | 03: 2033-2037 (inclusive) | GCC; existing MATs | Qualifying sites to contribute to new provision on identified site |  | Yes | Agreed in principle
Moreton-in-Marsh | All sites | 1.312 | North Cotswold new Secondary | 6FE Secondary school (with contributions in line with mitigation / support wider re-distribution of students travelling to Chipping Camden) to be delivered at Moreton in Marsh | 01_Education | 01_Secondary | IDP modelling | Essential | See see site totals to avoid double counting | GCC Education (Benchmark per Secondary pupil of £29,875 for 900) for £26,887,500 | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs | Qualifying sites to contribute to new provision on identified site |  | Yes | Agreed in principle
Ampney Crucis | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | 1.313 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 2270500 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 1.314 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 2569250 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 1.315 | Secondary Financial contributions | Financial contributions provided to deliver onsite secondary school | 01_Education | 01_Secondary | IDP modelling | Essential | 6034750 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 1.316 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 2718625 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | 1.317 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 1643125 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 1.318 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 7289500 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 1.319 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 4809875 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 1.32 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 5019000 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 1.321 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 3734375 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | 1.322 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 5437250 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 1.323 | Secondary Financial contributions | Financial contributions provided to deliver onsite secondary school | 01_Education | 01_Secondary | IDP modelling | Essential | 8663750 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
North Cotswold | North Cotswold Sub area | 1.324 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 6393250 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs | To note sub area also includes consideration of Non-strategic allocations in sub area |  | Yes | Agreed in principle
South Cotswold | South Cotswold Sub area | 1.325 | Secondary Financial contributions | Financial contributions provided to deliver offsite secondary school as identified in IDS | 01_Education | 01_Secondary | IDP modelling | Essential | 10262361.25 | GCC Education (Benchmark per Secondary pupil of £29,875. Subject to pupil yield at application stage | 0 | S106; DfE grant | 07: Phased in line with delivery | GCC; existing MATs | To note sub area also includes consideration of Non-strategic allocations in sub area |  | Yes | Agreed in principle
District-wide | All sites | 1.41 | Post 16 education contribution | Contribution to strategic pot to support delivery of post 16 education | 01_Education | 01_Post 16 | IDP modelling | Important | 22675125 | GCC Education (Benchmark per post pupil of £29,875 for total of 759 places) | N/A | Section 106 | 07: Phased in line with delivery | GCC; existing MATs |  |  | Yes | Agreed in principle
District-wide | All sites | 2.111 | Reinforcement of existing community space | Existing provision well served to be reinforced where required and for schemes which do not deliver their own community facilities. This could include improvement of service offer and installation of Community Public Access Defibrillators (CPADs) | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | Included in CIL | N/A | N/A | CIL | 07: Phased in line with delivery | Parish and Town Councils | Where strategic sites are identified to required the provision of new community facilities, they are encouraged to liase with existing facilities to ensure alingment and collaboration where possible, including through combined facilities where appropriate |  | No | Draft for comment
Ampney Crucis | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | 2.112 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils | This is in excess of modelled need but considered to be the minimum viable size of amulti-functional community building and is otherwise required to support modelled mode share | Requirement below identified IDP minimum viable site of 400sqm but identified in transport requirements as onsite use | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 2.113 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. This will cover both local plan and beyond plan period growth scenario | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils | Cost estimate dependent on specification and subject to refinement. Broad order of magnitude costs provided to ensure considered at viability testing but subject to refinement at application stage. | Viability to review estimated costs as taken from project comparables | No | Draft for comment
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 2.114 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 500sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1500000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | 2.115 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils | This is in excess of modelled need but considered to be the minimum viable size of amulti-functional community building and is otherwise required to support modelled mode share | Requirement below identified IDP minimum viable site of 400sqm but identified in transport requirements as onsite use | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 2.116 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 600sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1800000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 2.117 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 600sqm to cover both the current Local Plan and the broad location for growth. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1800000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 2.118 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 2.119 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. At this stage this is considered to be the smallest viable community facility but subject to refinement at application stage | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | 2.12 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 400sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1200000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 2.121 | New onsite multifunctional community hub | A combined facility (covering community, culture, blue light and potential indoor sport requirement) of approximately 600sqm. | 02_Community and social infrastructure | 02_Multifunctional community space | IDP modelling | Important | 1800000 | BCIS estimate of £2,640/m² + fees (£3,000) for outside London combined facility applied to facility size, including fit out but excluding land cost | 0 | S106; direct delivery | 02: 2027-2037 (inclusive) | Parish and Town Councils |  |  | No | Draft for comment
District-wide | All sites | 2.21 | Reinforcement of existing Library provision to support current Local Plan growth | Current preferred option is the expansion/relocation of the Moreton-in- Marsh Library. The alternatives (a staellite site of collection point in a multifunctional community building) provides a pragmatic and sustainable alternatives, enabling access to core library services without the requirement for dedicated on-site staff at all times. Such facilities can deliver a meaningful library presence within new communities, supporting access to resources, digital inclusion, and reading engagement. Both options could offer a range of services, including (but not limited to): • A curated lending stock • Self-service kiosks for issuing and returning items • Book reservation and collection services • Public access computers • Printing and associated digital services These models offer flexibility in terms of location and design. Provision could be situated within a dedicated room or integrated into a shared community space, such as a hub, leisure facility, or café area | 02_Community and social infrastructure | 02_Library | IDP modelling | Important | 2976848 | GCC Developer Guide | 0 | S106 | 07: Phased in line with delivery | GCC Libraries | Alternative sites for new sites will also be supported but subject to retention of existing staffing levels |  | Yes | Agreed in principle
Cirencester | All sites | 2.31 | Expansion of Stratton Cemetery | Potential expansion of Stratton Cemetery - provision of land in kind of CIL | 02_Community and social infrastructure | 02_Burial ground/cemeteries | CDC Bereavement team | Important | Included in CIL | Establishment costs are proprtional to build out with largest barrier being the land transfer costs associated with adjacent land owner (BDL) | 0 | CIL | 05: 2033-2043 (inclusive) | CDC Bereavement team |  |  | No | Draft for comment
North Cotswold | North Cotswold Sub area | 3.11 | Land to support new GP surgery/ existing Business Cass | Support Chipping Camden Surgery -expanded current future funding commitment- part of overall plan need for circa 30,000 patients and 2,500sqm requirement | 03_Primary Healthcare | 03_GP space | IDP modelling | Important | Planning obligation | N/A | Business case approved covering operational costs | CIL | 01: 2027-2032 (inclusive) | GCC ICB; NHS | Cost assumed to be based on provision of land to support current business case approval and not a direct financial contribution beyond wider CIL |  | Yes | Agreed in principle
Cirencester | Circencester Sub area | 3.12 | Land to support new GP surgery/ existing Business Cass | Support replacement of Pheonix Health surgery (moving from Chesterton Lane)- Expansion space at the marginal rate preferred option. Part of overall plan need for circa 30,000 patients and 2,500sqm requirement. Currently envisaged to be delivered on existing Steadings site or as part of Southern Expansion | 03_Primary Healthcare | 03_GP space | IDP modelling | Important | Planning obligation | N/A | Business case approved covering operational costs | CIL | 01: 2027-2032 (inclusive) | GCC ICB; NHS | Cost assumed to be based on provision of land to support current business case approval and not a direct financial contribution beyond wider CIL |  | Yes | Agreed in principle
Cirencester | Circencester Sub area | 3.13 | Identify land to support new GP surgery/ existing Business Cass | Support expansion of Cirencester Neighbourhood health centre - Specific site to be identified in Cirencester sub area, preliminarily identified as Land at Kingshill - part of overall plan need for circa 30,000 patients and 2,500sqm requirement. | 03_Primary Healthcare | 03_GP space | IDP modelling | Important | Planning obligation | N/A | Business case approved covering operational costs | CIL | 01: 2027-2032 (inclusive) | GCC ICB; NHS | Alternative locations would also be considered on their merits but Kingshill benefits from the need for onsite facilities to support modal share and access to existing patient lists in Cirencester |  | Yes | Agreed in principle
Moreton-in-Marsh | Moreton-in-Marsh Sub area | 3.14 | Contributions towards feasibility testing of expansions for Moreton-In-Marsh existing facility | Support with feasibility testing and potential expansion of the existing Moreton-in-Marsh surgery | 03_Primary Healthcare | 03_GP space | IDP modelling | Important | Included in CIL | N/A | N/A | CIL | 02: 2027-2037 (inclusive) | GCC ICB; NHS |  |  | No | Agreed in principle
District-wide | All sites | 3.15 | Seek opportunities to provide a Neighbourhood Health Centre | Subject to business case work being prepared but the scheme is supported by CDC | 03_Primary Healthcare | 03_GP space | IDP modelling | Important | Included in CIL | N/A | N/A | CIL | 07: Phased in line with delivery | GCC ICB; NHS |  |  | No | Agreed in principle
District-wide | All sites | 4.11 | Compliance with onsite open space standards | Covering Accessible Green Space, Allotments and Play in particular | 04_Open space and Sports | 04_Onsite Open space standards | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 07: Phased in line with delivery | CDC Policy team; management companies | Costs considered covered by site delivery costs |  | No | Agreed in principle
District-wide | All sites | 4.21 | Sport hall CUAs | Support continued Community Use Agreements of sports halls, particularly in Cirencester and as part of new Educational facilities | 04_Open space and Sports | 04_Sport and recreation | Sport England | Important | Included in CIL | N/A | N/A |  | 04: 2038-2043 (inclusive) | Multi-academy trusts, CDC Leisure, Sports England, National Governing Boards |  |  | No | Agreed in principle
District-wide | All sites | 4.31 | KKP playing pitch report conclusions | Contributions to increase carrying capacity of existing facilities | 04_Open space and Sports | 04_Sport and recreation | KKP Playing Pitch Strategy | Important | Included in CIL | N/A | N/A | CIL | 07: Phased in line with delivery | CDC Leisure, Sports England, National Governing Boards |  | CDC to provide latest KKP work | Yes | Draft for comment
District-wide | All sites | 4.32 | KKP playing pitch report conclusions | Local Plan wide need for 18 playing pitches | 04_Open space and Sports | 04_Sport and recreation | KKP Playing Pitch Strategy | Important | 3334236.9231 | KKP evidence base for pitch cost, calculated across plan period. | N/A |  | 07: Phased in line with delivery | CDC Leisure, Sports England, National Governing Boards, Strategic Sites | Scope of cost dependent on need identified at application stage. It is envisaged these will be delivered on the strategic sites in full although standalone sites will be supported | CDC to provide latest KKP work | Yes | Draft for comment
South Cotswold | South Cotswold Sub area | 4.41 | Beechwood SAMM contribution | Contributions to SANG provided on strategic sites for qualifying homes (See SANG strategy) | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 955788.03 | Based on worst case for the inner zone - £836.21/unit (+ admin charge) based on applications from April 26, noting not all windfall will be qualifying dwellings in a ZoI | N/A |  | 07: Phased in line with delivery | Natural England; CDC |  | Specific figures to be added once SANG strategy finalised | Yes | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | 4.42 | Onsite SANG | Minimum size of x ha SANG | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | Planning obligation | N/A | N/A | Direct delivery | 01: 2027-2032 (inclusive) | Natural England | Considered covered by site delivery costs | Specific figures to be added once SANG strategy finalised | Yes | Agreed in principle
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | 4.43 | Onsite ANRG | Minimum size of x ha ANRG | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | Planning obligation | N/A | 0 | Direct delivery | 01: 2027-2032 (inclusive) | Natural England | Considered covered by site delivery costs | Specific figures to be added once SANG strategy finalised | Yes | Agreed in principle
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 4.45 | Onsite ANRG | Minimum size of x ha ANRG | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | Planning obligation | N/A | N/A | Direct delivery | 01: 2027-2032 (inclusive) | Natural England | Considered covered by site delivery costs | Specific figures to be added once SANG strategy finalised | Yes | Agreed in principle
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | 4.46 | Onsite SANG | Minimum size of x ha SANG | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | Planning obligation | N/A | N/A | Direct delivery | 01: 2027-2032 (inclusive) | Natural England | Considered covered by site delivery costs | Specific figures to be added once SANG strategy finalised | Yes | Agreed in principle
District-wide | All sites | 4.47 | Strategic Local Plan SANG to serve non-strategic and windfall sites | Potential need for residual SANG provision to mitigate impact of windfall, saved allocations and non-strategic allocations of circa 19ha. Could be provided as part of strategic sites, or an alterative potential strategic location for Local Plan SANG. This has preliminarily been identified adjacent to the Kemble Strategic Site but would be paid for by qualifying development | 04_Open space and Sports | 04_SANG provision | LUC SANG Strategy | Essential | 0 | Potential to be delivered as a commercial enterprise | N/A | Direct delivery | 01: 2027-2032 (inclusive) | Natural England; CDC | Alternative sites will also be supported | Specific figures to be added once SANG strategy finalised | Yes | Agreed in principle
District-wide | All sites | 6.11 | Fibre to the premises | FTTP expectation for all schemes over 10 homes | 06_Utilities | 06_Digital | GCC developer guide | Important | Planning obligation | N/A | Full costs | Likely funded by Universal Service Obligation | 07: Phased in line with delivery | Openreach |  |  | No | Agreed in principle
District-wide | All sites | 6.21 | Reinforcement of electricity supply | Scale of reinforcement dependent on wider energy transition. Requirements likely to be triggered in early stages of the local plan (0-5 years) and therefore early engagement is required to determine scale of upgrade required once Local Plan is found sound. Specific schemes identified as supporting scale of growth identified seperately | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | 0 | N/A | 0 | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 01: 2027-2032 (inclusive) | SSEN |  |  | No | Draft for comment
District-wide | Circencester Sub area | 6.22 | Reinforcement of electricity supply | CIRENCESTER Bulk Supply Point (Earliest identified negative headroom [minimum headroom scenario] in future projection occurs in 2031) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 01: 2027-2032 (inclusive) | SSEN |  | To be refined with statuory providers | No | Draft for comment
District-wide | All sites | 6.23 | Reinforcement of electricity supply | STRATTON (RESERVE) Bulk Supply Point (Earliest identified negative headroom [minimum headroom scenario] in future projection occurs in 2029) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 01: 2027-2032 (inclusive) | SSEN |  | To be refined with statuory providers | No | Draft for comment
District-wide | South Cotswold Sub area | 6.24 | Reinforcement of electricity supply | MELKSHAM Grid Supply point (Earliest in service date for applications >1MW in 2036) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 03: 2033-2037 (inclusive) | SSEN | To note it is estimated that the Melksham GSP currently serves nearly 250,000 customers and is in the process of being upgraded | To be refined with statuory providers | No | Draft for comment
District-wide | North Cotswold Sub area | 6.25 | Reinforcement of electricity supply | COWLEY Grid Supply point (Earliest in service date for applications >1MW in 2029) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 01: 2027-2032 (inclusive) | SSEN | To note it is estimated that the Cowley GSP currently serves nearly 270,000 customers and is in the process of being upgraded | To be refined with statuory providers | No | Draft for comment
District-wide | All sites | 6.26 | Reinforcement of electricity supply | Minety Grid Supply point (Earliest in service date for applications >1MW in 2036) | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 02: 2027-2037 (inclusive) | SSEN | To note it is estimated that the Minety GSP currently serves nearly 150,000 customers and is in the process of being upgraded | To be refined with statuory providers | No | Draft for comment
North Cotswold | North Cotswold Sub area | 6.27 | Reinforcement of electricity supply | Moreton-in-Marsh Primary substation | 06_Utilities | 06_Electricity supply | IDP modelling | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan | 02: 2027-2037 (inclusive) | National Grid/Western Power |  | To be refined with statuory providers | No | Draft for comment
Cirencester | Circencester Sub area | 6.31 | Cirencester STW | Cirencester - Will be approaching its permit limit towards the end of the plan period and would only have 5% headroom left in 2045. As a result, it will likely require planned upgrades within the plan period | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Critical | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 06: 2027-2043 (inclusive) | Thames water |  | To be refined with statuory providers | No | Draft for comment
Fairford | Fairford Sub area | 6.32 | Fairford STW works | Fairford - Expected to require additional capacity between 2030 and 2035 | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 01: 2027-2032 (inclusive) | Thames water |  | To be refined with statuory providers | No | Draft for comment
Mickleton | Mickleton Sub area | 6.33 | Honeybourne STW | Honeybourne - Expected to require additional capacity between 2040 and 2045 | 06_Utilities | 06_Water Supply and Wastewater | Severn Trent | Critical | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 04: 2038-2043 (inclusive) | Severn Trent |  | To be refined with statuory providers | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh Sub area | 6.34 | Moreton in Marsh STW | Moreton-in-Marsh - Expected to require additional capacity between 2030 and 2035 | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Critical | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 01: 2027-2032 (inclusive) | Thames water |  | To be refined with statuory providers | No | Draft for comment
North Cotswold | North Cotswold Sub area | 6.35 | Blockley STW | Blockley STW is currently at or close to capacity and could impact windfall development | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 01: 2027-2032 (inclusive) | Thames water |  | To be refined with statuory providers | No | Draft for comment
South Cotswold | Multiple: Ampney St Peter STW | 6.36 | Ampney St Peter | Ampney St Peter - Expected to require additional capacity between 2030 and 2035 | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 01: 2027-2032 (inclusive) | Thames water |  | To be refined with statuory providers | No | Draft for comment
South Cotswold | South Cotswold Sub area | 6.37 | Lechlade STW | Lechlade - Will be approaching its permit limit towards the end of the plan period and would only have 7% headroom left in 2045. As a result, it will likely require planned upgrades within the plan period | 06_Utilities | 06_Water Supply and Wastewater | Thames Water | Essential | TBC | TBC | TBC | Infrastructure Charge; Statutory Undertaker Assets Management Plan; water industry price review | 04: 2038-2043 (inclusive) | Thames water |  | To be refined with statuory providers | No | Draft for comment
District-wide | All sites | 7.11 | Consolidation of blue light facilities | Support in the delivery of shared services and hubs and in existing Community Fire Stations, in line with the GFRS 'Productivity and Efficiency Plan 2025-2026' | 07_Emergency services | 07_Fire and rescue | IDP modelling | Important | Included in CIL | N/A | CIL | S106; CIL; National funding | 07: Phased in line with delivery | Gloucestershire Constabulary; SW Ambulance Service; Gloucestershire Fire and Rescue | Identified through a number of strategic plans but not specific project identified as required to deliver the local plan growth |  | No | Draft for comment
District-wide | All sites | 7.12 | Support for consolidation of existing facilities and inclusion within multi-functional community hubs provided on strategic sites |  | 07_Emergency services | 07_Police | IDP modelling | Important | Covered separately under multifunctional communty hub costs | N/A | N/A | S106; CIL; National funding | 07: Phased in line with delivery | Gloucestershire Constabulary; SW Ambulance Service; Gloucestershire Fire and Rescue | Costs included in estimates for multifunctional community building |  | No | Draft for comment
District-wide | All sites | 7.21 | On site provision of hydrants | Requirement for on site hydrant provision for schemes over 50 homes and on selected commercial developments. Where local fire risk could be demonstrably heightened, the provision for modern suppression in appropriate homes to reduce call outs will be sought | 07_Emergency services | 07_Fire and rescue | GCC developer guide | Important | Planning obligation | N/A | N/A | Direct delivery | 07: Phased in line with delivery | Gloucstershire Fire and Rescure | Scale of obligation considered to be covered by site development costs |  | No | Agreed in principle
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | 7.31 | New Community Response post |  | 07_Emergency services | 07_Ambulance | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 02: 2027-2037 (inclusive) | SW Ambulance Trust | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | 7.32 | New Community Response post |  | 07_Emergency services | 07_Ambulance | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 02: 2027-2037 (inclusive) | SW Ambulance Trust | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | 7.33 | New Community Response post |  | 07_Emergency services | 07_Ambulance | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 02: 2027-2037 (inclusive) | SW Ambulance Trust | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | 7.34 | New Community Response post |  | 07_Emergency services | 07_Ambulance | IDP modelling | Important | Planning obligation | N/A | N/A | Direct delivery | 02: 2027-2037 (inclusive) | SW Ambulance Trust | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
District-wide | All sites | 8.11 | On site SUDS | To meet local plan standards | 08_Flood Management | 08_Onsite mitigation | SFRA | Essential | Planning obligation | N/A | N/A | Direct delivery | 07: Phased in line with delivery | Strategic site promoter | Scale of obligation considered to be covered by site development costs |  | No | Draft for comment
Cirencester | Circencester Sub area | 8.12 | Natural Flood Mitigation scheme | Catchment north of Cirencester | 08_Flood Management | 08_Offsite mitigation | LLFA | Important | TBC | N/A | 0 | S106; CIL; EA | 04: 2038-2043 (inclusive) | GCC LLFA |  | To check if still appetite to support at CDC and GCC- retained from previous IDP | No | Draft for comment
Ampney Crucis | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | Ac1 | On site provision of services | This site represents a significant expansion of an existing village to the north. At present there is extremely limited services around the village including a small village hall, a small primary school (~100 pupils), a small play park and green space and a small church. The level development (660 dwellings) combined with the more isolated nature of the site (~5miles from Cirencester which is likely to be where most services are for the housing). It is approximately 2-2.5 miles from the Driffield Site. The scale of the development suggests that it would require at least an additional primary school, a retail offering ideally with a sizable convenience shop and/or postal facilities collection/delivery and a third space such as community centre | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Ampney Crucis | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | Ac2 | Enhancements to 50 Bus | Currently the 50 bus provides a circularly route between Cirencester and Ampney Crucis Monday to Friday between 8:50 13:50. This intervention will increase the frequency of the bus from hourly to half-hourly and extend the times to 0730 to 1830 (to allow for work time commuting). In addition services would run a more limited service on Saturday and Sunday (at present there is no services. Given the level of current provision an additional vehicle would likely be needed. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 01: 2027-2032 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Ampney Crucis | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | Ac3 | Active Travel route to join D7 (access to Down Ampney, Driffield Site and Cirencester) | An active travel route including cycling and walking to join onto intervention D7 to provide a route between all the major sites and Cirencester. This route is 2.1km long and would be formed through small bit of shared pathway on the A417 between Village Street and Waterton Farm (BAC25 footpath) 0.4km followed by 1.7km of upgraded footpath to shared space. Explicitly Dependent on D7, Cir4, Cir5, CIr7 and CIr8 being delivered | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Ampney Crucis | Ampney Crucis Sub Area | Ac4 | Ampney Cruicis-Poulton-Fairford Active Travel Route | An active travel route providing a route to Poulton including Ampney St Peter. 3.4km predominantly upgraded bridleways, footpaths and tracks followed by 1.3km of quiet lane treatment, 1.6km of on road segregation followed by 3.2km of quiet lane treatment on Welsh Way. The whole route is 8.6km. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 4000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Ampney Crucis | Ampney Crucis Sub Area | Ac5 | Amney Cruicis 20mph zone | 20mph within Ampney Crucis including new residential streets, village street, school lane, butchers arm lane, allotment lane, and riding lane (from the northern edge of the site to Ashbrook lane junction) | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Ampney Crucis | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | Ac6 | Diversion of 77 through Village Street | Diversion of the 76/77 bus route through Ampney Crucis. This will provide bus services to Fairford and additional services to Circencester | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 01: 2027-2032 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Ampney Crucis | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | Ac7 | Segregated Active Travel Route on Access Road and B4425 | Route along new access road and then extend and enhance segregated cycleway within road boundary, | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 2500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir10 | Siddington Road Cycleway | Provision of an on-road cycleway connecting Sites SD23 and SD17 to town centre via Siddington Road. Cycleway would follow Siddington Road then turn onto Kingsmead Road to connect to existing cycleway underpass under Bristol Road. To be delivered along with Cir5 to provide onwards cycle access to town centre. | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 300000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir11 | Extend London Road cycleway | Extend London Road cycleway next to Site C81B toward town centre with on-road cycle lane. Connect to existing active travel bridge over Swindon Road, creating a shared use path for pedestrians and cyclists. Rejoin cycleway to London Road and towards town centre with | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Kemble Sub area | Cir12 | Enhancement to 882 bus service | Increase the frequency of the Stagecoach West 882 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 01: 2027-2032 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir14 | Cirencester mobility hub | Development of a new or enhanced mobility hub integrating public transport, micromobility, cycle facilities, and shared mobility options | 05_Transport | 05_Supporting Sustainable transport integration | Cotswold DC | Essential | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | All sites | Cir15 | Cirencester Park and Ride | Park and ride/stride provision to intercept car trips at the edge of town, with potential for targeted bus priority measures to improve reliability and attractiveness of services into Cirencester. Park and Rides tend to target cars coming from out of town. Given the placement of this it is unlikely to be used by sites within the local plan. It is will be important for reducing overall traffic levels which may help local plan traffic however at present the modelling does not suggest it is critical for the functioning of the network | 05_Transport | 05_Public transport - Bus | Cotswold DC | Important | 10000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 04: 2038-2043 (inclusive) | Bus provider, GCC |  | To be raised with GCC. City Science identify this is difficult evidence in model. GCC and WSP working on this as a project but considered difficult to link to LP sites. If retained, we would suggest this is raised to be a more significant priority. | No | Draft for comment
Cirencester | Circencester Sub area | Cir16 | Wayfinding improvements | Introduction of a coherent, high-quality wayfinding strategy to improve navigation, reinforce key destinations, and enhance the legibility of walking and cycling networks across the town. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Important | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 05: 2033-2043 (inclusive) | GCC; Town and Parish Councils |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir17 | East-West Pedestrian / Cycle route improvements | Strengthening east–west pedestrian and cycle connectivity across Cirencester, improving continuity, safety, and accessibility. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Important | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir18 | Tesco–Siddington Road Active Travel Link | Creation of a direct, safe walking and cycling route connecting Tesco to Siddington Road, improving local accessibility and reducing short car trips. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Essential | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 05: 2033-2043 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir19 | Orchard Fields–Steadings Active Link | Establishment of a walking and cycling route through Orchard Fields connecting Siddington to The Steadings. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Essential | 375000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 05: 2033-2043 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir2 | Spratsgate Lane/Somerfield Road active travel links | Package of active travel measure could include providing pedestrian footpaths for residents willing to walk into Cirencester, as well as a on-road segregated cycleway. Require active travel access points along Spratsgate Lane for Sites SD20 and C190 | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir20 | Siddington–South Cerney active travel link | Development of a strategic active travel corridor utilising the disused railway line to provide a direct, segregated walking and cycling link between Siddington and South Cerney. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Essential | 1100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir21 | Green Lane Quiet Road | Reclassification of Green Lane (off Clark’s Lane) from highway use to a quiet lane with lower speed limits and appropriate signage to enable shared use road for walking and cycling. | 05_Transport | 05_Active travel / public realm | Cotswold DC | Essential | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir22 | A417 Underpass Roundabouts Active Travel Mitigation | Model suggests that cycling along the Dower's Lane becomes unsuitable for most people from suitable for some people due to increased traffic volumes. Many surrounding roads are currently assessed to have low suitability for cycling however there are a few off-road routes nearby meaning some cycle routing may be happening. Mitigation is likely to involve speed limit treatment on Dower's Lane and a shared pathway/cyclops upgrade to the two roundabouts. There is limited suitability in the wider area for cycling so this is unlikely to be a critical mitigation | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  | This has been adjusted slightly keeping only the underpass as this is still a problem and acts as the only AT way across the A417. The price remains constant because the section lost was very minor speed limit changes. | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir23 | Spratsgate Lane AT Mitigation | At present the road has minimal segregated infrastructure (with the exception of the new roundabout that feeds into the development near the Wilkinson Road Junction). The change is traffic is significant enough that even with minimal interventions such as 20mph zones and traffic calming or non-segregated cycle lanes are unlikely to be sufficient to leave the road suitable for most people. At present this route lies on the National Route 45. Multiple options should be explored including providing segregated provision or through alternative routing for the key routes that may use this route. For example K10 intervention may open up a route through Chesterton Farm and into the town centre and to east provision could be improved for a route along love lane. These interventions would be in addition to that proposed as part of the committed steadings site. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir24 | On site provision of services | Site further from Cirencester Town centre require on site provision of essential services to reduce travel in to the town centre. This should include at a minimum a primary school, a community space, a retail offering (ideally a small convenience store and service for last mile delivery such a RM parcel box and parcel collection (either within a retail offering or through an external parcel collection service). | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir25 | Kingshill Road/London Road mitigation | Upgrade Junction to a signalised Junction​ | 05_Transport | 05_Highways | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir26 | Kingshill Road/Cirencester Road mitigation | Upgrade Junction to a signalised Junction​ | 05_Transport | 05_Highways | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Siddington -Strategic- Land south west of Siddington (1x landowner / promoter) | Cir27 | Somerford Road/Chesterton Lane HW Mitigation | Upgrade intersection between Somerford road and Chesterton lane to be signalised. The modelling suggests that increased traffic on Chesterton road will lead to severe queueing on the Somerford road due to them being unable to merge | 05_Transport | 05_Highways | City Science modelling | Essential | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir28 | Cirencester Road AT Flag | Limit issues for active travel using speed limits (20mph) and soft segregation | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 |  | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Ampney Crucis - Strategic - Ampney Crucis (1x landowner) | Cir29​ | B4425/A429 Stow Road mitigation ​ | Signal Optimisation/ Increase cycle time (reduce amount of loss time for Cherrytree Ln and increase green time B4425 and Stow Rd)​ Required to deal with harm to network​ | 05_Transport | 05_Highways | City Science modelling | Critical | 50000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir3 | Active travel access Swindon Road | Active travel access onto Swindon Road at the northeastern corner of Site R519 to give access to existing cycleway crossing the A419 and along Cricklade Road to town centre. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 200000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir30 | Cirencester-Swindon BRT | Implementation of BRT route prosed between Cirencester and Swindon. This is assumed to contain enough bus priority interventions to keep the journey times down and a service that is frequent a minimum of every fifteen minutes. In order to maximise the utility of these route for the local plan it is assumed that this will be an express stopping service that would call at Swindon-Down Ampney-Driffield Junction- Preston-Kingshill Lane-Cirencester. This captures around 2300 dwellings in the local plan. Journey time between Swindon and Cirencester should be no longer than 50-60 minutes to provide a competitive journey time to driving. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 5000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir32 | Enhanced or extended bus service between Site C187 via the Steadings to Cirencester | Increase the frequency of existing bus routes or implementation of a new bus route to connect the new site south of the Steadings via The Steadings to Cirencester. Could include a bus gate to permit bus movements between the Steadings and site C187. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC | Scheme requires alignment between saved allocation and Steadings Phase 2 |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir33 | Local transport corridor interchange hub in The Steadings | Implement a Local Transport Corridor Interchange Hub within The Steadings where bus service between The Steading and Cirencester will stop on site. | 05_Transport | 05_Supporting Sustainable transport integration | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 1000000 | S106 | 01: 2027-2032 (inclusive) | Bathhurst Development Ltd; GCC | Existing scheme being delivered by the Steading existing allocation and included as an assumption in the baseline transport modelling |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir34 | 20mph zones | Extended the 20mph zones to cover residential street and development sites. This follows the consultation currently out | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Essential | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir35 | Active Travel Route from South Steadings to Tetbury Road Entrance of Agricultural College | Route following the existing planned interconnection between the Steadings and South Steadings extension. Exiting on the southern access from the Steadings (assuming the roundabout has been designed with adequate segregation. Then 0.2km of shared pathway on the north bound side of the road. Given the likely low volumes of both pedestrians and cyclists a 3m shared pathway would be sufficient and can be delivered within the HW boundary | 05_Transport | 05_Active travel / public realm | City Science/ GCC | Critical | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC; Agricultural College |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir36​ | A419 Swindon Road/Silver Street | Upgrade the junction to a signalised junction and add approach flares. | 05_Transport | 05_Highways | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir37 | A429/Chesterton Ln Junction​ | Change the stages and phases (having an all A429 stage followed by a Chesterton ln stage, and more green time for Stroud lane approach) ​ | 05_Transport | 05_Highways | City Science modelling | Critical | 50000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land south east of Cirencester and south of Preston (2x landowners / promoter) | Cir38 | A419 Stroud Road/Trewsbury Road | Upgrade the junction to a signalised junction and add approach flares. | 05_Transport | 05_Highways | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir39 | A429 Watermoor Roundabout | Add approach arm flares to the roundabout and widen the eastbound approach arm. | 05_Transport | 05_Highways | City Science modelling | Critical | 10000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir4 | Cricklade Road Cycleway Enhancement | Upgrade the cycleway from Preston Toll Bar along Cricklade Road by installing high-quality road surface throughout, introducing a designated on-road cycle lane, and implementing clear signage. Extend this cycleway improvements to the town centre, passing under the foot tunnel under the Bristol Road and joining Watermoor Way | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Steadings southern extension (1x landowner) | Cir40 | Stroud Road north of Tetbury Roundabout | Widen the road to two lanes to accommodate development access. | 05_Transport | 05_Highways | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways | Existing scheme being delivered by the Steading existing allocation and included as an assumption in the baseline transport modelling |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir41 | A419 Swindon Road\Cirencester Road | Widen the roundabout to provide two lanes between the roundabout and the Kingsmill Lane signalised junction. | 05_Transport | 05_Highways | City Science modelling | Critical | 10000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir42 | A29 Swindon Road/Bristol Road Roundabout | Widen the roundabout. | 05_Transport | 05_Highways | City Science modelling | Critical | 10000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Cirencester | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | Cir5 | Watermoor Road space reallocation | Reallocate road space along Watermoor Road to create a serrated cycleway, joining with Cycleway improvements in Cir4 to provide active travel links for southern development sites into Cirencester. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir7 | Active travel access on Kingshill Lane | Active travel access on western boundary of site directly opposite off road leading to Cirencester skate park. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Cirencester - Strategic - Land east of Kingshill Lane (1x landowner / promoter) | Cir8 | Queen Elizabeth Road/Beeches Road cycleway | On road cycleway connecting to existing east-west cycle route to link Sites R650 and R519 to town centre. Include on road cycleways along Queen Elizabeth Road and Beeches Road. Then a segregated cycle lane along London Road/Lewis Lane to access town centre. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Cirencester | Circencester Sub area | Cir9 | Pedestrianise Castle Street | Extend current pedestrian zone restrictions to on Crickade Road to cover Castle Street for more attractive placemaking in town centre. Reallocate road space to active travel infrastructure and green space. Divert East West traffic along Park Lane, Black Jack Street, Market Place and The Waterloo to reach London Road | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC; Town and Parish Councils |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D1 | On site provision of services | Site requires on-Site provision of key services such as retail and healthcare as there is currently only one small village shop in Down Ampney, with other retail and healthcare services located over 3km away. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D2 | Cricklade cycle route | Cycleway connecting Down Ampney and Cricklade to give sustainable access to retail services in Crickade. Route would follow Down Ampney Road and head south on Cirencester road, cross the A419 and continue down into Crickade. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 900000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D3 | South Cerney cycle route | Cycleway connecting Down Ampney and Cricklade to give sustainable access to retail services in South Cerney. Route would follow Down Ampney Road west and cross the A419, before turning north onto Cerney Wick Lane and following north on to Station Road into the centre of South Cerney. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1750000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Down Ampney | Multiple: SE Cirencester Strategic sites (South of Preston, Down Ampney and Driffield) | D4 | Driffield Junction Development cycle route | Cycleway connecting Down Ampney to Driffield Junction Development via existing bridleway to the north of the development Site. Route meets the eastern boundary of the Driffield Junction Development Site, where, in conjunction with Option DJ3 it would benefit from onwards cycle access to Cirencester. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  | City Science to review costs. Scheme is effectively the mechanism to deliver wider change to character to support the SE Cirencester sites | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D6 | Enhancements of 76 bus route | Increase the frequency of the Stagecoach West 76 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D7 | Down Ampney -Cirencester Greenway | Extended greenway linking Sites in Down Ampney to Cirencester. Route would extend up through the sites in Down Ampney, north along the PROW route (BDA1) and the west towards Driffield (Route BDD16). It would then connect with the sites at Driffield Junction Development, running directly through these sites and onwards to the existing bridleway running northeast from Harnhill and adjacent to the A419. It would cross the A417 at Witpit Lane and connect to the sites along Kingshill Lane. For there it would follow Cir8 into town centre. Explicity Dependent on Cir4, Cir5, CIr7 and CIr8 | 05_Transport | 05_Active travel / public realm | Cotswold DC | Critical | 3500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D9 | 20mph zones | Introducing 20mph zones across Down Ampney including within development sites | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Essential | 75000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | Direct delivery | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | D10 | Quiet Lane Treatment on Unnamed Road between Oak Road and Fairford Road | In order to limit the use of this not suitable single track road several measures are pursured: Speed limit Change from National Speed limit to 30mph - this change will ensure that suitabity level for active travel is improved as well as limit the perceived advantage of the route. Traffic calming measures including road marking and bumps. In addition formally designating this as a rural quiet lane with measures to ensure that traffic is kept beneath 1000 pcu a day. Finally in order to facilated passing more passing places to be implemented with | 05_Transport | 05_Highways | City Science modelling | Essential | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  | City Science Added | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ1 | On site provision of services | Site requires on-Site provision of key services such as retail, education and healthcare as closest services are 2 miles away in South Cerney or Down Ampney. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ10​ | B4696 Spine Rd Approach to Station Rd/Cerney Wick Ln Intersection​ | Upgrade Junction to a signalised Junction​ | 05_Transport | 05_Highways | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ2 | South Cerney active travel route | Provision of a segregated cycleway linking the western boundary of the Site to services in South Cerney for those who are able to cycle the distance. This could include active travel priority at A419/B4696 junction, then an onwards active travel route along the B4696 and Station Road into South Cerney. Alternatively could explore an active travel bridge over A419 connecting to and active trave route along Bow Wow Road directly into South Cerney. This assumed D3 is delivered | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 200000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ3 | Cirencester active travel route | Provision of a segregated cycleway connecting the Site to Cirencester via Cirencester Road for those able to cycle the distance. It is assumed that this should be delivered using a crossing of Cirencester Road which requires a change in the character of that road. GCC expressed support for this. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 3000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  | Yes -CS to comeback to this | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ5 | Driffield Junction Development Village Mobility Hub | A smaller mobility hub providing bus services, EV charging and parcel drop off points. | 05_Transport | 05_Supporting Sustainable transport integration | City Science modelling | Critical | 1500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Driffield | Driffield - Strategic - Land south of Driffield (2x landowners) | DJ8 | Bridleway enhancement to Down Ampney (Wiltshire) | Enhancement of Bridleways through Wiltshire to high quality cycleway and walking route to Down Ampney | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 750000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | Wilshire Highways | To note this scheme would be implemented outside of GCC highways boundary in Wiltshire |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa1 | On site provision of services | On-Site provision of key services such as retail and healthcare. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa10 | Enhancement to 76 bus service | Increase the frequency of the Stagecoach West 76 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 350000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Fairford | Fairford Sub area | Fa11 | Fairford High Street Placemaking and AT | Increased traffic from Local Plan developments lead the high street to become "unsuitable" for most people. At present the high street has dedicated a lot of space to private vehicle use including parking and minimal space to active travel. Possible solutions include limiting or removing through traffic from the high street, full pedestrianisation, a one way system in additional to the removal of parking to allow for more segregated routes. | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC Highways |  | This has been adjusted and kept in on vision grounds. There is also some evidence of an issue for active travel | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa12 | 20mph zones | Introducing 20mph zones across Down Ampney including within development sites | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa13 | Fairford-Lechlade AT Route | Segregated Cycleway on Park Street (0.3km) followed by quiet lane treatment (with physical calming measures) on Leafield Road (0.5km) followed by footway upgrade to shared space (0.4km), segregated route along Hatherop Lane (0.3km) and then again (shared) along to Slothop Road (2.2km) followed by enhanced of a bridleway (1.6km) finally quiet lane treatment on Hambidge Lane (2.7km). Cost is additional to Fa3 | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 800000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment . This scheme is dependent on Fa2 being delivered | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  | Linked to Fa2 - Delivery of Fa2 is a requirement of delivering this | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa2 | Southrop Road/London Road active travel route | Provision of a segregated active route linking Site F57C to the town centre via Southrop Road and London Road. Package of measures include ensuring filling in gaps in pedestrian infrastructure and ensuring continuous footpaths and adequate crossing facilities, as well as enabling a shared used road with a cycleway. Requires active travel access of the southern boundary of the large Site along Hatherop Road and active travel access of the northern boundary of the large Site south of Southrop road. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  | Costs have been reviewed and this is correct for only the portion this covers | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa3 | Hatherop Road active travel route | Provision of an active route connecting Site F57B to the town centre via Hatherop Road. Measures could include widening existing footpaths in some areas and, ensuing adequate crossing facilities and implementing shared used road with a cycleway. Requires active travel access to Site along northwestern boundary along Hatherop Road. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa5 | Cinder Lane quiet road | Designation of Cinder Lane as a quiet road, to encourage active travel from Site F20A to the Town centre. Requires active travel access to Cinder Lane on northern boundary of Site. Includes surfacing upgrade. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 380000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa6 | Horcott Road active travel route | Improve active travel links along Horcott Road to encourage sustainable access from Site F53A to the town centre. This includes by widen footpaths and improving crossing over wide-mouth junctions heading to town centre, as well as introducing a cycleway. This could connect to existing the cycleway crossing Dilly's Bridge and connecting to Gas Lane, providing a more direct route to High Street. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 620000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa8 | Leafield Road Crossing | Provision of pedestrian crossing connecting Site to the east of Leafield Road to the Primary School opposite. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 140000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | Multi-academy trust; GCC |  |  | No | Draft for comment
Fairford | Fairford - Strategic - Land north-east of Fairford (1x landowner) | Fa9 | Leafield Road active travel route | Providing footpaths along Leafield road and a shared space to enable active travel into town centre from Site F57A. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  | Reviewed and updated | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K10 | Kemble -Cirencester cycleway | Reuse of former rail route as a cycleway connecting Kemble and Cirencester for access to employment and education. | 05_Transport | 05_Active travel / public realm | GCC (LTP) | Critical | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K12 | Kemble to Tetbury Service bus service | New bus service connecting town centre of Kemble, developments Sites and Tetbury, along A439, Oxleaze Road and A433. Modelling suggests 100-200 passengers a day | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K13 | On site provision of services | Sites require on-site provision of key services such as retail and healthcare as there are minimal key services available in Kemble. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K14 | Windmill Road AT Mitigation | Flag identifies cycling may become unsuitable for most people as a result of increased traffic flow. At present the road is functionally not a full two-way street due to parking on the street. Mitigation could involve removing on street parking given most houses have drives to accommodate segregation | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 160000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K15 | Kemble to Ewen Cycle Mitigation | Model suggests that local plan traffic will make Windmill Road, School Road to Ewen no longer 'suitable for most people'. Mitigation involves shared pathway and reduction to 40mph | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 1100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K20 | 20mph zones | Introducing 20mph zones across all streets in Kemble, including within the development sites. | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K3 | Church Road active travel | Improvements to active travel along Church Road for Site K12. This includes active travel access to site boundary on Church road, continuous footways and possible exploration of a quiet lane on Church Road with lower speed limits and signage to improve mixed use of road for cycling. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K5 | Improved A429 crossing facilities | Improved active travel crossing facilities to allow active travel access from Site K12 to access Station Road, for onwards access to Kemble Station. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 100000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K6 | Station Road active travel | Improved pedestrian footways and cycleways along Station Road to promote active travel access from Sites K12 to Kemble Station | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 120000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | K8 | Kemble station improvements | Package of improvements including improving accessibility at the station with step free bridge, cycle parking etc. | 05_Transport | 05_Public transport - Rail | GCC (LTP) | Critical | 2500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | GWR, Network Rail |  |  | No | Draft for comment
Down Ampney | Down Ampney - Strategic - Land surrounding Down Ampney (2x landowners/ promoters) | LP10 | B4040/B4696 | Signal Optimisation | 05_Transport | 05_Highways | City Science modelling | Essential | 50000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | Wilshire Highways | To note this scheme would be implemented outside of GCC highways boundary in Wiltshire |  | No | Draft for comment
North Cotswold | North Cotswold Sub area | LP4 | Rail Level Crossings: Chipping Campden and Blockley Risk Flag | Increased traffic has the potential to impact the traffic on two level crossings on the rail network: Chipping Campden and Blockley. Mitigations may include safety upgrades | 05_Transport | 05_Public transport - Rail | City Science modelling | Critical | TBC | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | GWR, Network Rail |  | Level crossing no longer appear to flag as a risk. CS has not seen GWR formal response but if it suggests otherwise we have to revisit. These crossing were not flagged by GCC rail feedback | No | Draft for comment
Kemble | North Cotswold Sub area | LP7​ | Stow-on-the-Wold Sheep Street/A429/High Street Mitigation​ | Change signal stages with indicative arrows at high street/Roman Rd Junctions.​ Signal optimisation at A429/B4068. | 05_Transport | 05_Highways | City Science modelling | Critical | 130000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC Highways |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | LP8 | Avening High Street AT Mitigation | Model suggests that Avening High Street becomes unsuitable to most people to cycle on after the local plan. Mixed traffic suitability could be restored if the speed limit is reduced to 20mph with a corresponding amount of traffic calming to ensure the design speed matches the new speed limit. The remainder of links surrounding this one are deemed unsuitable according to LTN1/20 before and after the local plan which means this stretch is unlikely to currently form part of a whole route however there are some non-road routes near by which this may cut off. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Kemble | Kemble - Strategic - Land south-west of Kemble (1X landowner / promoter) | LP9 | Coates AT Mitigation | Model suggests that cycling on the Trewsbury Road becomes unsuitable for most people due to increased traffic volumes. Caveat: At present all the surrounding rounds into Coates are current deemed to be unsuitable for most cyclists and this is unlikely to block a route. Solutions include implementing a one way system around coates to allow for cycle lanes and/or speed reductions. | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic11 | 20mph zones | Introducing 20mph zones across all streets in Mickleton, including within the development sites. | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic2 | Site Active Travel Connections and wider offsite improvements to car-free routes | Active Travel only connections to the public park to provide attractive active travel routes within Mickleton. At present the paths within the park are not sufficient for cycling and so upgrade of widths for a shared pathway or separate cycling routes would be required. Includes at least 2.6km of pathways to upgrade | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  | Costs have been updated in line with the new stretch of paths treated | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic3 | Long Marsdon Road Active Travel Connection | Cycleway and/or Shared Pathways along Long Marsdon Road to facilitate segregated access to National Cycleway 5 route featuring a fully car-free travel route to Stratford-Upon-Avon the distance being approximated 12-14km/ 7.5-8.5 mi within the distance that some may commute especially if coupled with targeted e-micromobility interventions. | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | 3500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 03: 2033-2037 (inclusive) | GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic5 | On site provision of services | At present that are limited services within Mickleton itself. Providing a local hub including some GP services, Schools and Retail offerings and mobility hub | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic6 | Improved Bus Services Mickleton to Moreton-in-Marsh | Current services offer routes to Stratford-Upon-Avon, Chipping Campden and Moreton-In-Marsh. Frequency is approximately every one to two hours with early and late travel options available. No services exist to nearby Evesham. This intervention would look at improving frequency of the current offering whilst also adding connections to Evesham in line with new population. Nearby Warwickshire also has some sites nearby in REG18 so there is potential for collaboration. | 05_Transport | 05_Public transport - Bus | City Science modelling | Critical | 400000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic8 | Mickleton to Ebrington Primary School AT Flag | Baker's Hill, Hidcote Road are expected to become unsuitable to cycle. Part of the route sits on the existing national 42 cycle route. Mitigations that could be effective at retaining the cycle routes suitability include: 20mph along the stretch with included enforcement however this is unlikely to be viable across such a long stretch of rural road therefore share pathway segregation utilising bridleway for some of it. | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | Multi-academy trust; GCC |  |  | No | Draft for comment
Mickleton | Mickleton - Strategic - Land North and west of Mickleton (8 landowners / promoters) | Mic9 | Mickleton to Willersey speed route treatment | Reduction of Willersey Speed Limit to 20mph and "route treatment" to Mickleton. Could be potentially extended into Mickleton. | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Important | 75000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 75000 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo1 | Moreton-in-Marsh to Bourton-on-the-Water via Stow-on-the-Wold active travel link | An LTN1/20 compliant route from Moreton-In-Marsh to Bourton-on-the-Water via Stow-in-the-Wold. This route can either be in the form of a segregated addition to the Fosse Road or along the routes identified in the GCC countywide LCWIP (Evenload Road-Chapel Street-Ex railway alignment). The latter was estimated to need ~1-2million to deliver and the latter is assumed | 05_Transport | 05_Active travel / public realm | City Science/GCC LCWIP | Essential | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo10 | Moreton-in-Marsh New Road | South eastern portion of the link road around Moreton-in-Marsh to the East in an attempt to move through traffic and some development traffic away from currently constrained double roundabout. In order to remain inline with the vision to not induce increased car use this should include a wider array of measures including the potential to be car capacity neutral by e.g. pedestrianising or semi-pedestrianising the high street. | 05_Transport | 05_Highways | GCC/CDC/WSP | Critical | 37450252 | Bentley V2 costing report | 0 | S106; S278; Homes England forward funding | 02: 2027-2037 (inclusive) | GCC Highways; Strategic Site landowners | Delivery approach and cost based on the phased implementation of the access road across applications and aligned to the agreed masterplan, rather than pooled funding and delivery by GCC |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo12 | Moreton-In-Marsh to Chipping Campden Greenway | A quiet street and infrastructure approach to delivering a car-lite route from Moreton-In-Marsh to Chipping Campden. This largely would be upgrades the current 442 national cycle route and could include closure/one-way/speed treatments on one leg of the triangle near Batsford, work on the crossing at station road and lanes or shared pathways along areas of the road that can facilitate it. Alternatively a route could be pursued through upgrading of Rights of Way footpaths along the railway line via Paxford - this route is flatter but may be harder to deliver. Also to note that it opens up railway access for Chipping Campden including sites being delivered there | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo13 | Moreton-In-Marsh to Shipston-on-Stour Cycleway | Greenway from Moreton-in-Marsh to Shipstone-on-the-Stour. This could utilise the verge to make a shared pathway along Todenham Street and joining to an upgraded Bridleway to Shipston-on-Stour. It should be noted that there may be grounds for cross-collaboration over the border with development along this route | 05_Transport | 05_Active travel / public realm | City Science modelling | Essential | 1500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 04: 2038-2043 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo16 | Evenlode Improvements | Currently part of the National 48 and the 442 cycle routes and all cyclists are expected to mix with general traffic. The high amount of additional traffic from developments along the route means that cycling is likely to become unsuitable for most people. It is likely that to remain suitable some form of segregation is likely to be required. There is a marginal possibility that limiting speed along the road to 20mph as well with measures to decrease or reroute traffic may retain the route as suitable for some people | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 350000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo17 | Moreton-in-Marsh Station Improvements | Upgrades to the facilities of the station in line with high patronage including better active travel connections. | 05_Transport | 05_Public transport - Rail | City Science modelling | Critical | 3500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | GWR, Network Rail |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo18 | 20mph zones | Introducing 20mph zones across Moreton-in-Marsh (excluding A44 and A429) | 05_Transport | 05_Behaviour change | GCC (20mph Speed Work) | Critical | 150000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo2 | Blenheim Meadow AT routes upgrade | Upgrading the traffic-free paths through Blenheim Meadow to be suitable for cycling. Current paths cycling is not allowed and there are key barriers along the route. Upgrading these including widening and removal of barriers/gates will allow the developments further away from the centre to use cycling to access the town centre and railway station. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 250000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo3 | A44 Corridor Active Transport Route | From edge of Fire Service College Site to High Street roundabout on A44. A combination of measures including a shared pathway or pathway and cycleway up to the junction with Evenload Road where geometric constraint may need a different approach e.g. speed limit reductions or alternative routing. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo4 | Southern Moreton greenway | Footpaths HMM8 and HMM18 to be upgraded to shared green way and options explored to facilitate onwards routing in a low traffic environment, possibly through allotments and through quiet East Street. Facilitating traffic free travel from southern sites to town services. | 05_Transport | 05_Active travel / public realm | City Science modelling | Critical | 1000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 02: 2027-2037 (inclusive) | GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo5 | Moreton-in-Marsh to Cheltenham BRT | BRT Route C09/C08 Moreton-in-Marsh to Cheltenham | 05_Transport | 05_Public transport - Bus | WSP/GCC | Essential | 3500000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106 | 02: 2027-2037 (inclusive) | Bus provider, GCC |  |  | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo8 | Moreton-in-Marsh Transport Hub, parking and road space reallocation | Moving the predominant parking away from the High street to free up capacity on the road for other uses including any road adjustments required and a higher focus on placemaking activities and improved Active Travel facilities. It could include utilisation of parking pricing to further dis-incentivise the use of private vehicles. Includes "Park and Stride" facilities which are simply redistibuted parking away from high street with branding and guided walking routes to high street. | 05_Transport | 05_Active travel / public realm | City Science/Moreton-in-Marsh Neighbourhood Plan | Critical | 2000000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; S278 | 01: 2027-2032 (inclusive) | GCC; Town and Parish Councils |  | Updated costs and updated the detail to describe park and stride element | No | Draft for comment
Moreton-in-Marsh | Moreton-in-Marsh - Strategic - Land north, east and south of Moreton-in-Marsh (c. 14x landowners / promoters) | Mo9 | On site provision of services | On-Site provision of key services such as retail and healthcare. | 05_Transport | 05_Behaviour change | City Science modelling | Critical | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | N/A | Direct delivery | 02: 2027-2037 (inclusive) | Strategic site promoter |  |  | No | Draft for comment
District-wide | All sites | TBC | EV Charging Provision | Providing Additional EV charging infrastructure for public use in addition to provision within new homes, This could also feature incentives e.g. pricing to encourage uptake. | 05_Transport | 05_Behaviour change | City Science modelling | Important | Included in CIL | N/A | 0 | CIL | 07: Phased in line with delivery | GCC Highways |  |  | No | Draft for comment
District-wide | All sites | TBC | Travel Plan and Monitor and manage measures | smaller scale interventions to improve safety and implement TROs, improvements to expanded schools , additional bus stop infrastructure - identified where specified but to be derived by TAs | 05_Transport | 05_Behaviour change | Cotswold DC | Essential | Included in CIL | N/A | N/A | S106; S278; CIL | 07: Phased in line with delivery | GCC Highways |  |  | No | Draft for comment
Mickleton | Mickleton Sub area | TBC | Enhancements to North Cotswolds Robin Community Bus | Improving the frequency of The Robin within Mickleton. | 05_Transport | 05_Public transport - Bus | City Science modelling | Essential | Included in CIL | N/A | 0 | CIL | 07: Phased in line with delivery | GCC Highways |  |  | No | Draft for comment
Moreton-in-Marsh | North Cotswold Sub area | TBC | North Cotswold Line transformation | A series of improvements including doubling of the line leading to the a doubling of the frequency (to 2 trains per hour) and improved speed which would further make routes along this line such as Oxford-Worchester and London (and onto further connections) more time competitive with private modes. SOBC estimated the whole cost of this improvement to be £199 million but includes enabling of more housing in Oxfordshire so delivery could be partly delivered by this too. | 05_Transport | 05_Public transport - Rail | North Cotswold Line Taskforce | Regionally significant | 0 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | 0 | S106; CIL | 07: Phased in line with delivery | GWR, Network Rail | The Local Plan growth is not predicated upon the delivery of the Cotswold Line Transformation but is a project supported by CDC, who will consider using CIL to contribute to early feasibility work. |  | No | Draft for comment
District-wide | North Cotswold Sub area | XXMO1+ | Kingham Station-Stow-on-the-Wold-Bourton-On-The-Water Greenway | Active Travel route | 05_Transport | 05_Active travel / public realm | City Science modelling | Important | Included in CIL | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment | Included in CIL | CIL | 07: Phased in line with delivery | GCC | This scheme is supported as a wider aspiration but is not identified by the Local Plan evidence base as linked to proposed growth |  | No | Draft for comment
Kemble | Kemble Sub area | K21 | Anti-Ratrunning Measures on Unnamed Road between A429 and A433 | Minor alterations including speed interventions and no left turn into it from A429 and no right turn into it from A433 in order to stop traffic using to avoid A429/A433 junction | 05_Transport | 05_Highways | City Science modelling | Critical | 10000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment
North Cotswold | North Cotswold Sub area | LP16 | Willersey AT Flag | Willersey Leamington Road and Main Street because unsuitable for cycling due to increased traffic. 20mph speed limit would resolve this. | 05_Transport | 05_Highways | City Science modelling | Critical | 10000 | City Science estimate based on scheme typology and length of intervention. Additional details on methodology in Strategic Transport Assessment

## Package D 17-07-26
Option ID | Short title | Source | Description | Indicative High Level Cost | Evaluation of Intervention Importance to Local Plan | Status | Growth Area/Strategic Site
XXMO1+ | Kingham Station-Stow-on-the-Wold-Bourton-On-The-Water Greenway | AK CDC | Active Travel route | 2000000 | Important | Proposed | All
Ac1 | On-site services | City Science | This site represents a singificant expansion of an existing village to the north. At present there is extremely limited services around the village including a small village hall, a small primary school (~100 pupils), a small play park and green space and a small church. The level development (660 dwellings) combined with the more isolated nature of the site (~5miles from Cirencester which is likely to be where most services are for the housing). It is approximately 2-2.5 miles from the Driffield Site. The scale of the development suggests that it would require at least an additional primary school, a retail offering ideally with a sizable convience shop and/or postal facilities collection/delivery and a third space such as community centre | 0 | Critical | LP: On-site | Cotswold: Ampney Cruicis
Ac2 | Enhancements to 50 Bus | City Science | Currently the 50 bus provides a circularly route between Cirencester and Amney Cruicis Monday to Friday between 8:50 13:50. This intervention will increase the frequency of the bus from hourly to half-hourly and extend the times to 0730 to 1830 (to allow for work time commuting). In addition services would run a more limited service on saturday and sunday (at present there is no services. Given the level of current provision an additional vehicle would likely be needed. | 500000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Ac3 | Active Travel route to join D7 (access to Down Ampney, Driffield Site and Cirencester) | City Science | An active travel route including cycling and walking to join onto intervention D7 to provide a route between all the major sites and Cirencester. This route is 2.1km long and would be formed through small bit of shared pathway on the A417 between Village Street and Waterton Farm (BAC25 footpath) 0.4km followed by 1.7km of upgraded footpath to shared space. | 1000000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Ac4 | Ampney Cruicis-Poulton-Fairford Active Travel Route | City Science | An active travel route providing a route to Poulton including Ampney St Peter. 3.4km predominantly upgraded bridleways, footpaths and tracks followed by 1.3km of quiet lane treatment, 1.6km of on road segregation followed by 3.2km of quiet lane treatment on Welsh Way. The whole route is 8.6km. | 4000000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Ac5 | Amney Cruicis 20mph zone | City Science | 20mph within Ampney Cruicis including new residential streets, village street, school lane, butchers arm lane, alloment lane, and riding lane (from the northern edge of the site to ashbrook lane junction) | 100000 | Critical | LP: Local access | Cotswold: Ampney Cruicis
Ac6 | Diversion of 77 through Village Street | City Science | Diversion of the 76/77 bus route through Ampney Crucis. This will provide bus services to fairford and additional services to circencester | 100000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Ac7 | Segregated Active Travel Route on Access Road and B4425 | City Science | Route along new access road and then extend and enhance segregated cycleway within road boundary, | 2500000 | Critical | LP: Strategic (off-site) | Cotswold: Ampney Cruicis
Cir2 | Spratsgate Lane/Somerfield Road active travel links | City Science | Package of active travel measure could include providing pedestrian footpaths for residents willing to walk into Cirencester, as well as a on-road segregated cycleway. Require active travel access points along Spratsgate Lane for Sites SD20 and C190 | 1400000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir3 | Active travel access Swindon Road | City Science | Active travel access onto Swindon Road at the northeastern corner of Site R519 to give access to existing cycleway crossing the A419 and along Cricklade Road to town centre. | 200000 | Critical | LP: Local access | Cotswold: Cirencester
Cir4 | Cricklade Road Cycleway Enhancement | City Science | Upgrade the cycleway from Preston Toll Bar along Cricklade Road by installing high-quality road surface throughout, introducing a designated on-road cycle lane, and implementing clear signage. Extend this cycleway improvements to the town centre, passing under the foot tunnel under the Bristol Road and joining Watermoor Way | 2000000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir5 | Watermoor Road road space reallocation | City Science | Reallocate road space along Watermoor Road to create a serrated cycleway, joining with Cycleway improvements in Cir4 to provide active travel links for southern development sites into Cirencester. | 250000 | Critical | LP: Local access | Cotswold: Cirencester
Cir6 | Internal active travel links for Site R650 | City Science | Internal active links connecting Site R650 to Site R519 to benefit from active travel access towards town centre suggested in Cir4 and Cir5. | 0 | Critical | LP: Local access | Cotswold: Cirencester
Cir7 | Active travel access on Kingshill Lane | City Science | Active travel access on western boundary of site directly opposite off road leading to Cirencester skate park. | 150000 | Critical | LP: Local access | Cotswold: Cirencester
Cir8 | Queen Elizabeth Road/Beeches Road cycleway | City Science | On road cycleway connecting to existing east-west cycle route to link Sites R650 and R519 to town centre. Include on road cycleways along Queen Elizabeth Road and Beeches Road. Then a segregated cycle lane along London Road/Lewis Lane to access town centre. | 1000000 | Critical | LP: Local access | Cotswold: Cirencester
Cir9 | Pedestrianise Castle Street | City Science | Extend current pedestrian zone restrictions to on Crickade Road to cover Castle Street for more attractive placemaking in town centre. Reallocate road space to active travel infrastructure and green space. Divert East West traffic along Park Lane, Black Jack Street, Market Place and The Waterloo to reach London Road | 100000 | Important | LP: Strategic (off-site) | Cotswold: Cirencester
Cir10 | Siddington Road Cycleway | City Science | Provision of an on-road cycleway connecting Sites SD23 and SD17 to town centre via Siddington Road. Cycleway would follow Siddington Road then turn onto Kingsmead Road to connect to existing cycleway underpass under Bristol Road. To be delivered along with Cir5 to provide onwards cycle access to town centre. | 300000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir11 | Extend London Road cycleway | City Science | Extend London Road cycleway next to Site C81B toward town centre with on-road cycle lane. Connect to existing active travel bridge over Swindon Road, creating a shared use path for pedestrians and cyclists. Rejoin cycleway to London Road and towards town centre with | 500000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir12 | Enhancement to 882 bus service | City Science | Increase the frequency of the Stagecoach West 882 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 400000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir14 | Cirencester mobility hub | Cotswold DC | Development of a new or enhanced mobility hub integrating public transport, micromobility, cycle facilities, and shared mobility options | 1000000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir15 | Cirencester Park and Ride | Cotswold DC | Park and ride/stride provision to intercept car trips at the edge of town, with potential for targeted bus priority measures to improve reliability and attractiveness of services into Cirencester. Park and Rides tend to target cars coming from out of town. Given the placement of this it is unlikely to be used by sites within the local plan. It is will be important for reducing overal traffic levels which may help local plan traffic however at present the modelling does not suggest it is critical for the functioning of the network | 10000000 | Important | LP: Strategic (off-site) | Cotswold: Cirencester
Cir16 | Wayfinding improvements | Cotswold DC | Introduction of a coherent, high-quality wayfinding strategy to improve navigation, reinforce key destinations, and enhance the legibility of walking and cycling networks across the town. | 500000 | Important | LP: Strategic (off-site) | Cotswold: Cirencester
Cir17 | East-West Pedestrian / Cycle route improvements | Cotswold DC | Strengthening east–west pedestrian and cycle connectivity across Cirencester, improving continuity, safety, and accessibility. | 500000 | Important | LP: Strategic (off-site) | Cotswold: Cirencester
Cir18 | Tesco–Siddington Road Active Travel Link | Cotswold DC | Creation of a direct, safe walking and cycling route connecting Tesco to Siddington Road, improving local accessibility and reducing short car trips. | 250000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir19 | Orchard Fields–Steadings Active Link | Cotswold DC | Establishment of a walking and cycling route through Orchard Fields connecting Siddington to The Steadings. | 375000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir20 | Siddington–South Cerney active travel link | Cotswold DC | Development of a strategic active travel corridor utilising the disused railway line to provide a direct, segregated walking and cycling link between Siddington and South Cerney. | 1100000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir21 | Green Lane Quiet Road | Cotswold DC | Reclassification of Green Lane (off Clark’s Lane) from highway use to a quiet lane with lower speed limits and appropriate signage to enable shared use road for walking and cycling. | 100000 | Essential | LP: Strategic (off-site) | Cotswold: Cirencester
Cir22 | Dower's Lane and A417 Underpass Roundabouts Active Travel Mitigation |  | Model suggests that cycling along the Dower's Lane becomes unsuitable for most people from suitable for some people due to increased traffic volumes. Many surrounding roads are currently assessed to have low suitability for cycling however there are a few off-road routes nearby meaning some cycle routing may be happening. Mitigation is likely to involve speed limit treatment on Dower's Lane and a shared pathway/cyclops upgrade to the two roundabouts. There is limited suitability in the wider area for cycling so this is unlikely to be a critical mitigation | 250000 | Not Important | Proposed | Cotswold: Cirencester
Cir23 | Spratsgate Lane AT Mitigation | City Science | At present the road has minimal segregated infrastructure (with the exception of the new roundabout that feeds into the development near the Wilkinson Road Junction). The change is traffic is significant enough that even with minimal interventions such as 20mph zones and traffic calming or non-segregated cycle lanes are unlikely to be sufficient to leave the road suitable for most people. At present this route lies on the National Route 45. Multiple options should be explored including providing segregated provision or through alternative routing for the key routes that may use this route. For example K10 intervention may open up a route through Chesterton Farm and into the town centre and to east provision could be improved for a route along love lane. These interventions would be in addition to that proposed as part of the commited steadings site. | 1400000 | Critical | Proposed | Cotswold: Cirencester
Cir24 | On site provision of services | City Science | Site further from Cirencester Town centre require on site provision of essential services to reduce travel in to the town centre. This should include at a minimum a primary school, a community space, a retail offering (ideally a small convience store and service for last mile delivery such a RM parcel box and parcel collection (either within a retail offering or through an external parcel collection service). | 0 | Critical | LP: On-site | Cotswold: Cirencester
Cir25 | Kingshill Road/London Road mitigation | City Science | Targeted junction improvements to address capacity constraints and improve traffic flow. | 200000 | Critical | Proposed | Cotswold: Cirencester
Cir26 | Kingshill Road/Cirencester Road mitigation | City Science | Corridor-based measures to alleviate congestion and improve travel into and Cirencester. | 250000 | Critical | Proposed | Cotswold: Cirencester
Cir27 | Somerford Road/Chesterton Lane HW Mitigation | City Science | Upgrade intersection between somerford road and chesterton lane to be signalised. The modelling suggests that increased traffic on Chesterton road will lead to severe queueing on the Somerford road due to them being unable to merge | 250000 | Essential | Proposed | Cotswold: Cirencester
Cir28 | Cirencester Road AT Flag | Ciry Science | Limit issues for active travel using speed limits (20mph) and soft segregation | 400000 | Critical | 0 | Cotswold: Cirencester
Cir29​ | B4425/A429 Stow Road mitigation ​ | City Science | Signal Optimisation/ Increase cycle time (reduce amount of loss time for Cherytree Ln and increase green time B4425 and Stow Rd)​ Required to deal with harm to network​ | £10-50k​ | Critical | Proposed | Cotswold: Cirencester
Cir30 | Cirencester-Swindon BRT | City Science | Implementation of BRT route prosed between Cirencester and Swindon. This is assumed to contain enough bus priority interventions to keep the journey times down and a service that is frequent a minimum of every fifteen minutes. In order to maximise the utility of thise route for the local plan it is assumed that this will be an express stopping service that would call at Swindon-Down Ampney-Driffield Junction- Preston-Kingshill Lane-Cirencester. This captures around 2300 dwellings in the local plan. Journey time between Swindon and Cirencester should be no longer than 50-60 minutes to provide a competitive journey time to driving. | 5000000 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir31 | Active travel connections with and through The Steadings | City Science | Connection of Cirencester to Kemble active travel route to the south side of The Steading site, with active connections through the site to allow onwards active travel to Cirencester. | 0 | Critical | LP: Local access | Cotswold: Cirencester
Cir32 | Enhanced or extended bus service between Site C187 via the Steadings to Cirencester | City Science | Increase the frequency of existing bus routes or implementation of a new bus route to connect the new site south of the Steadings via The Steadings to Cirencester. Could include a bus gate to permit bus movements between the Steadings and site C187. | 150000 | Critical | BAU+ | Cotswold: Cirencester
Cir33 | Local transport corridor interchange hub in The Steadings | City Science | Implement a Local Transport Corridor Interchange Hub within The Steadings where bus service between The Steading and Cirencester will stop on site. | 0 | Critical | LP: Strategic (off-site) | Cotswold: Cirencester
Cir34 | 20mph zones | City Science | Extended the 20mph zones to cover residential street and development sites. This follows the consultation currently out | 150000 | Essential | LP: On-site | Cotswold: Cirencester
Cir35 | Active Travel Route from South Steadings to Tetbury Road Entrance of Agricultural College | City Science/ GCC | Route following the existing planned interconnection between the Steadings and South Steadings extension. Exiting on the southern access from the Steadings (assuming the roundabout has been designed with adequate segregation. Then 0.2km of shared pathway on the north bound side of the road. Given the likely low volumes of both pedestrians and cyclists a 3m shared pathway would be sufficient and can be delivered within the HW boundary | 100000 | Critical | LP: Local access | Cotswold: Cirencester
Cir36​ | A419 Swindon Road/Silver Street | City Science | Upgrade the junction to a signalised junction and add approach flares. | ~0.5-1million | Critical | Proposed | Cotswold: Cirencester
Cir37 | A429/Chesterton Ln Junction​ | City Science | Change the stages and phases (having an all A429 stage followed by a Chesterton ln stage, and more green time for Stroud lane approach) ​ | £10-50k​ | Critical | Proposed | Cotswold: Cirencester
Cir38 | A419 Stroud Road/Trewsbury Road | City Science | Upgrade the junction to a signalised junction and add approach flares. | ~0.5-1million | Critical | Proposed | East of Cirencester
Cir39 | A429 Watermoor Roundabout | City Science | Add approach arm flares to the roundabout and widen the eastbound approach arm. | £1-10million​ | Critical | Proposed | Cotswold: Cirencester
Cir40 | Stroud Road north of Tetbury Roundabout | City Science | Widen the road to two lanes to accommodate development access. | £1-10million​ | Critical | Proposed | Cotswold: Cirencester
Cir41 | A419 Swindon Road\Cirencester Road | City Science | Widen the roundabout to provide two lanes between the roundabout and the Kingsmill Lane signalised junction. | £1-10million​ | Critical | Proposed | Cotswold: Cirencester
Cir42 | A29 Swindon Road/Bristol Road Roundabout | City Science | Widen the roundabout. | £1-10million​ | Critical | Proposed | Cotswold: Cirencester
D1 | On site provision of services | City Science | Site requires on-Site provision of key services such as retail and healthcare as there is currently only one small village shop in Down Ampney, with other retail and healthcare services located over 3km away. | 0 | Critical | LP: On-site | Cotswold: Down Ampney
D2 | Cricklade cycle route | City Science | Cycleway connecting Down Ampney and Cricklade to give sustainable access to retail services in Crickade. Route would follow Down Ampney Road and head south on Cirencester road, cross the A419 and continue down into Crickade. | 900000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D3 | South Cerney cycle route | City Science | Cycleway connecting Down Ampney and Cricklade to give sustainable access to retail services in South Cerney. Route would follow Down Ampney Road west and cross the A419, before turning north onto Cerney Wick Lane and following north on to Station Road into the centre of South Cerney. | 1750000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D4 | Driffield Junction Development cycle route | City Science | Cycleway connecting Down Ampney to Driffield Junction Development via existing bridleway to the north of the development Site. Route meets the eastern boundary of the Driffield Junction Development Site, where, in conjunction with Option DJ3 it would benefit from onwards cycle access to Cirencester. | 1500000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D6 | Enhancements of 76 bus route | City Science | Increase the frequency of the Stagecoach West 76 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 1000000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D7 | Down Ampney -Cirencester Greenway | Cotswold DC | Extended greenway linking Sites in Down Ampney to Cirencester. Route would extend up through the sites in Down Ampney, north along the PROW route (BDA1) and the west towards Driffield (Route BDD16). It would then connect with the sites at Driffield Junction Development, running directly through these sites and onwards to the existing bridleway running northeast from Harnhill and adjacent to the A419. It would cross the A417 at Witpit Lane and connect to the sites along Kingshill Lane. For there it would follow Cir8 into town centre. | 3500000 | Critical | LP: Strategic (off-site) | Cotswold: Down Ampney
D9 | 20 mph zones | City Science | Introducing 20mph zones across Down Ampney including within development sites | 75000 | Essential | LP: Strategic (off-site) | Cotswold: Down Ampney
DJ1 | On site provision of services | City Science | Site requires on-Site provision of key services such as retail, education and healthcare as closest services are 2 miles away in South Cerney or Down Ampney. | 0 | Critical | LP: On-site | Cotswold: Driffield Junction Development
DJ2 | South Cerney active travel route | City Science | Provision of a segregated cycleway linking the western boundary of the Site to services in South Cerney for those who are able to cycle the distance. This could include active travel priority at A419/B4696 junction, then an onwards active travel route along the B4696 and Station Road into South Cerney. Alternatively could explore an active travel bridge over A419 connecting to and active trave route along Bow Wow Road directly into South Cerney. This assumed D3 is delivered | 200000 | Critical | LP: Strategic (off-site) | Cotswold: Driffield Junction Development
DJ3 | Cirencester active travel route | City Science | Provision of a segregated cycleway connecting the Site to Cirencester via Cirencester Road for those able to cycle the distance. It is assumed that this should be delivered using a crossing of Cirencester Road which requires a change in the character of that road. GCC expressed support for this. | 3000000 | Critical | LP: Strategic (off-site) | Cotswold: Driffield Junction Development
DJ5 | Driffield Junction Development Village Mobility Hub | City Science | A smaller mobility hub providing bus services, EV charging and parcel drop off points. | 1500000 | Critical | LP: Strategic (off-site) | Cotswold: Driffield Junction Development
DJ6 | Charlham Lane access | City Science | Active travel access to Charlham Lane to facilitate onward active travel to Primary school and shop. Much of this is covered by D4 but this just ensures the access is secured in the masterplan | 0 | Critical | LP: Local access | Cotswold: Driffield Junction Development
DJ8 | Bridleway enhancement to Down Ampney (Wiltshire) | City Science | Enhancement of Bridleways through Wiltshire to high quality cycleway and walking route to Down Ampney | 750000 | Critical | LP: Strategic (off-site) | Cotswold: Driffield Junction Development
DJ9 | Future Proofing for Post-Local Plan Growth | City Science | Ensuring that internal design accounts for future post-local growth particularly around the prevention of through-traffic | 0 | Critical | LP: On-site | Cotswold: Driffield Junction Development
DJ10​ | B4696 Spine Rd Approach to Station Rd/Cerney Wick Ln Intersection​ | City Science | Upgrade Junction to a signalised Junction​ | 250000 | Critical | Proposed | Cotswold: Driffield Junction Development
Fa1 | On-site provision of services | City Science | On-Site provision of key services such as retail and healthcare. | 0 | Critical | LP: On-site | Cotswold: Fairford
Fa2 | Southrop Road/London Road active travel route | City Science | Provision of a segregated active route linking Site F57C to the town centre via Southrop Road and London Road. Package of measures include ensuring filling in gaps in pedestrian infrastructure and ensuring continuous footpaths and adequate crossing facilities, as well as enabling a shared used road with a cycleway. Requires active travel access of the southern boundary of the large Site along Hatherop Road and active travel access of the northern boundary of the large Site south of Southrop road. | 0 | Critical | LP: Local access | Cotswold: Fairford
Fa3 | Hatherop Road active travel route | City Science | Provision of an active route connecting Site F57B to the town centre via Hatherop Road. Measures could include widening existing footpaths in some areas and, ensuing adequate crossing facilities and implementing shared used road with a cycleway. Requires active travel access to Site along northwestern boundary along Hatherop Road. | 2000000 | Critical | LP: Local access | Cotswold: Fairford
Fa4 | Trubshaw Way active travel access | City Science | Active travel access to Trubshaw Way for Site F20A for onward active travel to town centre. | 0 | Critical | LP: On-site | Cotswold: Fairford
Fa5 | Cinder Lane quiet road | City Science | Designation of Cinder Lane as a quiet road, to encourage active travel from Site F20A to the Town centre. Requires active travel access to Cinder Lane on northern boundary of Site. Includes surfacing upgrade. | 380000 | Critical | LP: Local access | Cotswold: Fairford
Fa6 | Horcott Road active travel route | City Science | Improve active travel links along Horcott Road to encourage sustainable access from Site F53A to the town centre. This includes by widen footpaths and improving crossing over wide-mouth junctions heading to town centre, as well as introducing a cycleway. This could connect to existing the cycleway crossing Dilly's Bridge and connecting to Gas Lane, providing a more direct route to High Street. | 620000 | Critical | LP: Local access | Cotswold: Fairford
Fa7 | E End active travel access | City Science | Provision of an active travel access from the western boundary of the Site F20A, enhancing the existing footpath the connects to E End | 0 | Critical | LP: Local access | Cotswold: Fairford
Fa8 | Leafield Road Crossing | City Science | Provision of pedestrian crossing connecting Site to the east of Leafield Road to the Primary School opposite. | 140000 | Critical | LP: Local access | Cotswold: Fairford
Fa9 | Leafield Road active travel route | City Science | Providing footpaths along Leafield road and a cycleway to enable active travel into town centre from Site F57A. | 0 | Critical | LP: Local access | Cotswold: Fairford
Fa10 | Enhancement to 76 bus service | City Science | Increase the frequency of the Stagecoach West 76 bus service to run once an hour to provide better public transport connectivity to Cirencester. | 350000 | Critical | LP: Strategic (off-site) | Cotswold: Fairford
Fa12 | 20mph zones | City Science | Introducing 20mph zones across Down Ampney including within development sites | 150000 | Critical | LP: On-site | Cotswold: Fairford
Fa13 | Fairford-Lechlade AT Route | City Science | Segregated Cycleway on Park Street (0.3km) followed by quiet lane treatment (with physical calming measures) on Leafield Road (0.5km) followed by footway upgrade to shared space (0.4km), segregated route along Hatherop Lane (0.3km) and then again (shared) along to Slothop Road (2.2km) followed by enhanced of a bridleway (1.6km) finally quiet lane treatment on Hambidge Lane (2.7km). Cost is additional to Fa3 | 800000 | Essential | LP: Strategic (off-site) | Cotswold: Fairford
K1 | A429 Active travel route | City Science | The A429 is the single route currently connecting the K15 sites to Kemble centre. Provide a segregated cycleway along road to improve active travel access to key services and schools in Kemble centre, along with improved continuous footpaths. | 0 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K2 | Access to Old Vicarage Lane | City Science | Active travel access to the south of Old Vicarage Lane of the eastern boundary of Site K12 to allow onwards active travel access to centre of Kemble. | 0 | Critical | LP: Local access | Cotswold: Kemble
K3 | Church Road active travel | City Science | Improvements to active travel along Church Road for Site K12. This includes active travel access to site boundary on Church road, continuous footways and possible exploration of a quiet lane on Church Road with lower speed limits and signage to improve mixed use of road for cycling. | 250000 | Critical | LP: Local access | Cotswold: Kemble
K5 | Improved A429 crossing facilities | City Science | Improved active travel crossing facilities to allow active travel access from Site K12 to access Station Road, for onwards access to Kemble Station. | 100000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K6 | Station Road active travel | City Science | Improved pedestrian footways and cycleways along Station Road to promote active travel access from Sites K12 to Kemble Station | 120000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K8 | Kemble station improvements | GCC (LTP) | Package of improvements including improving accessibility at the station with step free bridge, cycle parking etc. | 2500000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K21 | Anti-Ratrunning Measures on Unnamed Road between A429 and A433 | City Science | Minor alterations including speed interventions and no left turn into it from A429 and no right turn into it from A433 in order to stop traffic using to avoid A429/A433 junction | 10000 | Critical |  | Cotswold: Kemble
LP7​ | Stow-on-the-Wold Sheep Street/A429/High Street Mitigation​ | City Science | Change signal stages with indicative arrows at high street/Roman Rd Junctions.​ Signal optimisation at A429/B4068. | ~£90-130k​ | Critical | Proposed
LP8 | Avening High Street AT Mitigation | City Science | Model suggests that Avening High Street becomes unsuitable to most people to cycle on after the local plan. Mixed traffic suitability could be restored if the speed limit is reduced to 20mph with a corresponding amount of traffic calming to ensure the design speed matches the new speed limit. The remainder of links surrounding this one are deemed unsuitable according to LTN1/20 before and after the local plan which means this stretch is unlikely to currently form part of a whole route however there are some non-road routes near by which this may cut off. | 150000 | Critical | Proposed | Cotswold: Kemble
LP9 | Coates AT Mitigation | City Science | Model suggests that cycling on the Trewsbury Road becomes unsuitable for most people due to increased traffic volumes. Caveat: At present all the surrounding rounds into Coates are current deemed to be unsuitable for most cyclists and this is unlikely to block a route. Solutions include implementing a one way system around coates to allow for cycle lanes and/or speed reductions. | 150000 | Essential | Proposed | Cotswold: Kemble
LP10 | B4040/B4696 | City Science | Signal Optimisation | £10-50k​ | Essential | Proposed | In Wiltshire
LP16 | Willersey AT Flag | City Science | Willersey Leamington Road and Main Street because unsuitable for cycling due to increased traffic. 20mph speed limit would resolve this. | 10000 | Critical |  | North Cotswold
K10 | Kemble -Cirencester cycleway | GCC (LTP) | Reuse of former rail route as a cycleway connecting Kemble and Cirencester for access to employment and education. | 2000000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K12 | Kemble to Tetbury Service bus service | City Science | New bus service connecting town centre of Kemble, developments Sites and Tetbury, along A439, Oxleaze Road and A433. Modelling suggests 100-200 passengers a day | 400000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
K13 | On site provision of services | City Science | Sites require on-site provision of key services such as retail and healthcare as there are minimal key services available in Kemble. | 0 | Critical | LP: On-site | Cotswold: Kemble
K14 | Windmill Road AT Mitigation | City Science | Flag identifies cycling may become unsuitable for most people as a result of increased traffic flow. At present the road is functionally not a full two-way street due to parking on the street. Mitigation could involve removing on street parking given most houses have drives to accommodate segregation | 160000 | Critical | Proposed | Cotswold: Kemble
K15 | Kemble to Ewen Cycle Mitigation | City Science | Model suggests that local plan traffic will make Windmill Road, School Road to Ewen no longer 'suitable for most people'. Mitigation involves shared pathway and reduction to 40mph | 1100000 | Essential | Proposed | Cotswold: Kemble
K20 | 20mph zones | City Science | Introducing 20mph zones across all streets in Kemble, including within the development sites. | 150000 | Critical | LP: Strategic (off-site) | Cotswold: Kemble
Mic2 | Site Active Travel Connections and wider offsite improvements to car-free routes | City Science | Active Travel only connections to the public park to provide attractive active travel routes within Mickleton. At present the paths within the park are not sufficient for cycling and so upgrade of widths for a shared pathway or separate cycling routes would be required | 50000 | Critical | LP: Local access | Cotswold: Mickleton
Mic3 | Long Marsdon Road Active Travel Connection | City Science | Cycleway and/or Shared Pathways along Long Marsdon Road to facilitate segregated access to National Cycleway 5 route featuring a fully car-free travel route to Stratford-Upon-Avon the distance being approximated 12-14km/ 7.5-8.5 mi within the distance that some may commute especially if coupled with targeted e-micromobility interventions. | 3500000 | Important | LP: Strategic (off-site) | Cotswold: Mickleton
Mic5 | Mickleton Local Centre and Services Hub | City Science | At present that are limited services within Mickleton itself. Providing a local hub including some GP services, Schools and Retail offerings and mobility hub | 0 | Critical | LP: On-site | Cotswold: Mickleton
Mic6 | Improved Bus Services Mickleton to Moreton-in-Marsh | City Science | Current services offer routes to Stratford-Upon-Avon, Chipping Campden and Moreton-In-Marsh. Frequency is approximately every one to two hours with early and late travel options available. No services exist to nearby Evesham. This intervention would look at improving frequency of the current offering whilst also adding connections to Evesham in line with new population. Nearby Warwickshire also has some sites nearby in REG18 so there is potential for collaboration. | 400000 | Critical | LP: Strategic (off-site) | Cotswold: Mickleton
Mic8 | Mickleton to Ebrington Primary School AT Flag | City Science | Baker's Hill, Hidcote Road are expected to become unsuitable to cycle. Part of the route sits on the existing national 42 cycle route. Mitigations that could be effective at retaining the cycle routes suitability include: 20mph along the stretch with included enforcement however this is unlikely to be viable across such a long stretch of rural road therefore share pathway segregation utilising bridleway for some of it. | 2000000 | Essential | Proposed | Cotswold: Mickleton
Mic9 | Mickleton to Willersey speed route treatment | GCC (20mph Speed Work) | Reduction of Willersey Speed Limit to 20mph and "route treatment" to Mickleton. Could be potentially extended into Mickleton. | 0 | Important | LP: Strategic (off-site) | Cotswold: Mickleton
Mic11 | 20mph zones | City Science | Introducing 20mph zones across all streets in Mickleton, including within the development sites. | 150000 | Critical | LP: Strategic (off-site) | Cotswold: Mickleton
Mo1 | Moreton-in-Marsh to Bourton-on-the-Water via Stow-on-the-Wold active travel link | City Science/GCC LCWIP | An LTN1/20 compliant route from Moreton-In-Marsh to Bourton-on-the-Water via Stow-in-the-Wold. This route can either be in the form of a segregated addition to the Fosse Road or along the routes identified in the GCC countywide LCWIP (Evenload Road-Chapel Street-Ex railway alignment). The latter was estimated to need ~1-2million to deliver and the latter is assumed | 2000000 | Essential | Proposed | Cotswold: Moreton-In-Marsh
Mo2 | Blenheim Meadow AT routes upgrade | City Science | Upgrading the traffic-free paths through Blenheim Meadow to be suitable for cycling. Current paths cycling is not allowed and there are key barriers along the route. Upgrading these including widening and removal of barriers/gates will allow the developments further away from the centre to use cycling to access the town centre and railway station. | 250000 | Critical | LP: Local access | Cotswold: Moreton-In-Marsh
Mo3 | A44 Corridor Active Transport Route | City Science | From edge of Fire Service College Site to High Street roundabout on A44. A combination of measures including a shared pathway or pathway and cycleway up to the junction with Evenload Road where geometric constraint may need a different approach e.g. speed limit reductions or alternative routing. | 1500000 | Critical | LP: Local access | Cotswold: Moreton-In-Marsh
Mo4 | Southern Moreton greenway | City Science | Footpaths HMM8 and HMM18 to be upgraded to shared green way and options explored to facilitate onwards routing in a low traffic environment, possibly through allotments and through quiet East Street. Facilitating traffic free travel from southern sites to town services. | 1000000 | Critical | LP: Local access | Cotswold: Moreton-In-Marsh
Mo5 | Moreton-in-Marsh to Cheltenham BRT | WSP/GCC | BRT Route C09/C08 Moreton-in-Marsh to Cheltenham | 3500000 | Essential | BAU+ | Cotswold: Moreton-In-Marsh
Mo8 | Moreton-in-Marsh Transport Hub, parking and road space reallocation | City Science/Moreton-in-Marsh Neighbourhood Plan | Moving the predominant parking away from the High street to free up capacity on the road for other uses including any road adjustments required and a higher focus on placemaking activities and improved Active Travel facilities. It could include utilisation of parking pricing to further dis-incentivise the use of private vehicles. Includes "Park and Stride" facilities. | 2000000 | Critical | BAU+ | Cotswold: Moreton-In-Marsh
Mo9 | On-site services | City Science | On-Site provision of key services such as retail and healthcare. | 0 | Critical | LP: On-site | Cotswold: Moreton-In-Marsh
Mo10 | Moreton-in-Marsh New Road | GCC/CDC/WSP | South easten portion of the link road around Moreton-in-Marsh to the East in an attempt to move through traffic and some development traffic away from currently constrained double roundabout. In order to remain inline with the vision to not induce increased car use this should include a wider array of measures including the potential to be car capacity neutral by e.g. pedestrianising or semi-pedestrianising the high street. | ??? | Critical | Proposed | Cotswold: Moreton-In-Marsh
Mo12 | Moreton-In-Marsh to Chipping Campden Greenway | City Science | A quiet street and infrastructure approach to delivering a car-lite route from Moreton-In-Marsh to Chipping Campden. This largely would be upgrades the current 442 national cycle route and could include closure/one-way/speed treatments on one leg of the triangle near Batsford, work on the crossing at station road and lanes or shared pathways along areas of the road that can facilitate it. Alternatively a route could be pursued through upgrading of Rights of Way footpaths along the railway line via Paxford - this route is flatter but may be harder to deliver. Also to note that it opens up railway access for Chipping Campden including sites being delivered there | 1000000 | Essential | LP: Strategic (off-site) | Cotswold: Moreton-In-Marsh
Mo13 | Moreton-In-Marsh to Shipston-on-Stour Cycleway | City Science | Greenway from Moreton-in-Marsh to Shipstone-on-the-Stour. This could utilise the verge to make a shared pathway along Todenham Street and joining to an upgraded Bridleway to Shipston-on-Stour. It should be noted that there may be grounds for cross-collaboration over the border with development along this route | 1500000 | Essential | LP: Strategic (off-site) | Cotswold: Moreton-In-Marsh
Mo16 | Evenlode Improvements | City Science | Currently part of the National 48 and the 442 cycle routes and all cyclists are expected to mix with general traffic. The high amount of additional traffic from developments along the route means that cycling is likely to become unsuitable for most people. It is likely that to remain suitable some form of segregation is likely to be required. There is a marginal possibility that limiting speed along the road to 20mph as well with measures to decrease or reroute traffic may retain the route as suitable for some people | 350000 | Critical | LP: Local access | Cotswold: Moreton-In-Marsh
Mo17 | Moreton-in-Marsh Station Improvements | City Science | Upgrades to the facilities of the station in line with high patronage including better active travel connections. | 3500000 | Critical | LP: Strategic (off-site) | Cotswold: Moreton-In-Marsh
Mo18 | 20 mph zones | City Science | Introducing 20mph zones across Moreton-in-Marsh (excluding A44 and A429) | 150000 | Critical | LP: Strategic (off-site) | Cotswold: Moreton-In-Marsh
Note on F74: Assumed delivered as part Fa13
Note on F78: Assumed delivery as part of Masterplan

## SANG-ANRG spread
2026-07-06
Development type | New homes proposed | Occupation (2.2) | Area of SANG required (ha) | Area of ANRG required (ha)
Non-strategic; non-principal settlements | 188 | 414 |  | 0.18
Non-strategic; principal settlements | 425 | 935 | 1.6
Saved allocations from 2011-31 Local Plan | 96 | 211 | 1.69
Strategic Site | 9491 | 20880 | 28.23 | 68.29
Windfall | 1264 | 2781 | 15.54 | 1.8
Grand Total | 11464 | 25,221* | 47.06 | 70.26
|  | Amount outside SS | 18.83 | 1.98